Contract

No.  279485/2019-ČRA

Entered into on the below-mentioned day, month and year by and between:

### Contracting Authority: 	Czech Republic—Czech Development Agency

Represented by: 		Ing. Pavel Frelich, Director

Registered office: 		Nerudova 3, 118 50 Praha 1, Czech Republic

Contact person:		XXXXXXXXXXX

Phone: 			XXXXXXXXXXX

E-mail: 			XXXXXXXXXXX

Company ID no.: 		75123924

Bank connection: 		Czech National Bank, Na Příkopě 28, Praha 1, Czech Republic

Account number: 		0000 – 72929011/0710

(hereinafter the “Contracting Authority”)

And

Supplier: 			HY – Engineering PLC

Represented by: 		Henok Tsegaye Tadese, General Manager

Registered office:		Hawassa city, Tabore sub city, Hitata kebele, P.O. Box 538

Tax ID no.: 			0057735915

Bank connection: 	XXXXXXXXXXX

Account number: 	XXXXXXXXXXX

SWIFT code:			XXXXXXXXXXX

Supplier’s contact person: XXXXXXXXXXX

Phone: 		XXXXXXXXXXX

E-mail: 		XXXXXXXXXXX

(hereinafter the “Supplier”)

# Article 1

# Subject-matter of Contract

1. The Supplier hereby undertakes to carry out duly at its costs and on its liability for the Contracting Authority the work specified in Article 2 hereof.

2. The Contracting Authority hereby undertakes to pay the Supplier duly and in time for the performance of the work the agreed remuneration under the terms and conditions laid down by this Contract.

3. The parties have further agreed that this Contract also applies to all other activities and services carried out and provided by the Supplier in connection with the subject-matter of this Contract.

# Article 2

# Work

The work for the purposes of this Contract means the development of complete project documentation in English language - five Detail Designs for five community water supply systems - which will subsequently be used for the construction of new water supply systems for Tula and Shoye/Dageya kebeles  in Dale woreda, Hamesho kebele in Bensa woreda and Woreta Woyo and Awaye Keraro kebeles in Bona Zuriya woreda, Sidama zone, SNNPR, within the project „Improving quality of life by ensuring availability and sustainable management of water resources in Sidama Zone“. The work is specified in detail in Annex no. 1 of the Contract titled “Procedure of implementing the public contract”.

# Article 3

# Time Plan

The parties have explicitly agreed that the work must be completed by no later than 30 September 2019.

# Article 4

# Price of Work and Payments

1. The parties have agreed that the Contracting Authority shall pay the Supplier for the performance of the work under Article 2 hereof remuneration in the total amount of USD 46,380.87 (in words: forty-sixthousandthreehundredeightydollarsandeighty-sevencents), including VAT. The parties have agreed that the Contracting Authority shall pay the Supplier for:

- Tula Detail Design amount of USD 11,595.22 (in words: eleventhousandfive hundredninety-fivedollarsandtwenty-twocents), including VAT;

- Shoye/Dageya Detail Design amount of USD 9,276.17 (in words: ninethousandtwohundredseventy-sixdollarsandseventeencents), including VAT;

- Hamesho Detail Design amount of USD 13,914.26 (in words: thirteenthousandninehundredfourteendollarsandtwenty-sixcents), including VAT;

- Woreta Woyo Detail Design amount of USD 4,638.09 (in words: fourthousandsixhundredthirty-eightdollarsandninecents), including VAT:

- Awaye Keraro Detail Design amount of USD 6,957.13 (in words: sixthousandninehundredfifty-sevendollarsandthirteencents), including VAT.

The remuneration also covers all the costs arising to the Supplier in connection with the performance of the work.

2. The remuneration shall be paid to the Supplier after the completion of the work and its handover under Article 7 hereof on the basis of an invoice issued by the Supplier after the completion of the work and its handover to the Contracting Authority.  After completion of each Detail Design and its handover under Article 7 the Supplier can request payment of part of the remuneration corresponding to the value of the Detail Design stated in Article 4 paragraph 1 of this Contract. Payment of part of the remuneration is possible on the basis of an invoice issued by the Supplier.

3. The Contracting Authority will provide advance payment to the Supplier in the amount of 20 % of the total contracted amount, based on the request for advance payment. The Supplier will send a request for advance payment to the Contracting Authority within 14 days from the signature of the contract. The Supplier is obliged to carry out respective activities corresponding to the amount of advance payment within two months after receiving the advance payment. The Supplier shall prove to the Contracting Authority that activities corresponding to the amount of advance payment were finished within three months after receiving the advance payment by submitting final version of project documentation for one Detail Design or by submitting draft of project documentation for one Detail Design. If the Supplier fails to prove fulfilment of above stated obligation within this period, the advance payment must be returned to the Contracting Authority by bank transfer made within 10 days.

4. The request for the final payment and advance payment shall be admissible only if accompanied by the relevant invoice issued by the Supplier. The invoice shall always be delivered electronically to the Contracting Authority’s herein specified email address. In the invoice the Supplier shall state the project code ET-2017-020-FO-14030/3, sector: water and sanitation. The request for the final payment or payment of part of the remuneration according to paragraph 2 is admissible only if accompanied by handover protocol under Article 7 hereof.

5. The maturity period is 21 days from the delivery of the invoice to the Contracting Authority. The date of payment means the day when the payment is subtracted from the Contracting Authority’s account. The invoice must have all the essentials required of such document. The Contracting Authority may return an invoice to the Supplier within the maturity date without making any payment if the invoice contains incorrect data or if the handover protocol under Article 7 hereof is not submitted.

# Article 5

# Obligations of the Supplier

1. The Supplier is obligated to perform duly and in time all its obligations arising from this Contract.

2. The Supplier is especially liable for:

- ensuring the compliance of the work with the applicable legal regulations;

- implementation of the work in the required quality;

- implementation of the work in time within the deadlines specified herein or by Contracting Authority’s instructions.

3. The Supplier is not liable for any delay in the consequence of the Contracting Authority's failure to give assistance under Article 6 hereof.

# Article 6

# Obligations of the Contracting Authority

The Contracting Authority is obligated to give the Supplier the necessary assistance for the performance of the subject-matter of the Contract. Regarded as necessary assistance for the purposes of this Contract is in particular:

a) provision of all information and materials, at disposal to the Contracting Authority, which are directly related to the subject-matter of this Contract within no later than three working days after the relevant request, unless agreed otherwise between the parties;

b) designation of persons to cooperate with the Supplier for the entire time of the performance of the Contract who will be able to comment in a qualified manner on the situations, questions and requirements, if any, connected with the performance of the Contract.

# Article 7

# Acceptance of Work

- The parties have agreed that the work shall be handed over and approved by the Contracting Authority on the basis of a handover protocol signed by both of the parties. The parties will confirm completion and handover of each Detail Design by signing of handover protocol.

- Upon the signature of handover protocols for all Detail Designs the work shall be deemed duly performed, that is, completed and handed over to the Contracting Authority. This provision does not in any way limit the Contracting Authority's claims arising from liability for potential legal or factual defects of the work as defined in the applicable provisions of Civil Code and this Contract.

# Article 8

# Compensation of Damage, Contractual Penalties

1. The parties have explicitly agreed that for the purposes of damage compensation under this Contract loss of profits shall not be regarded as damage and therefore none of the parties shall demand any compensation of a loss of profits.

2. The parties have agreed that in the event of Supplier’s delay with due implementation and handover of the work to the Contracting Authority within the deadline specified in Article 3 hereof the Supplier shall pay the Contracting Authority a contractual penalty in the amount of USD 25 for each day of the delay with the fulfilment of this obligation.

3. The parties have agreed that in the event of Contracting Authority’s delay with due and timely payment of the price of the work pursuant to the provision of Article 4 hereof the Contracting Authority shall pay the Supplier a contractual penalty in the amount of 0.05% of the unpaid price of the work for each day of the delay with the fulfilment of this obligation.

# Article 9

# Dispute Resolution

The parties have further agreed that in the event of a dispute or a suspected or actual violation of the terms and conditions hereof they shall at first try in good faith together to settle the matter between themselves and only after this option turns out unproductive, they shall bring the matter before a court with the subject-matter and jurisdiction of the Czech Republic.

# Article 10

# Termination of Contract

The effectiveness of this Contract may be terminated:

- by a written agreement of the parties;

- either of the parties to this Contract may withdraw from this Contract after having granted the other party in writing a time limit of thirty (30) days for the rectification of identified defects or unfulfilled obligations arising from this Contract if the party which receives such notice fails to rectify the breach within the granted time limit of thirty (30) days which commenced on the day of the delivery of such notice. The Contract is terminated by withdrawal on the day when a written withdrawal notice is delivered to the other party. The parties have explicitly agreed that if the addressee is not reached or refuses to accept the consignment and confirm in writing the acceptance, the consignment shall be deemed delivered on the third day after its deposition;

- the Contracting Authority may withdraw from this Contract without stating a reason. The notice period is fifteen days and commences upon the delivery of the notice to the Supplier.

# Article 11

# General and Final Provisions

1. The parties declare that this Contract is entered into between them genuinely and freely, not in duress or under noticeably disadvantageous conditions.

2. Should this Contract have any legal defects, in particular if any of its provisions is in conflict with valid legal regulations, which might result in a situation when this Contract is deemed invalid, such provision shall be regarded as separate (and therefore separately invalid) and the Contract shall be viewed as if it has never contained such provision.

3. Unless explicitly agreed otherwise in this Contract, the relationships between the parties under this Contract shall be governed by the laws of the Czech Republic. The parties agree that the local court is the general court of the Contracting Authority.

4. This Contract may only be changed by a numbered written amendment signed by the authorized agents of both of the parties.

5. Neither party is liable for any delay or non-performance due to circumstances beyond its control.

6. This Contract constitutes an entire agreement between the parties and substitutes all prior agreements, arrangements and communications regarding the work. No other agreements, declarations, guarantees or other matters, whether oral or written, shall be deemed binding on the said parties in connection with the subject-matter of this Contract.

7. All notices and other communications delivered under this Contract must be made in writing and they become effective upon their delivery to the relevant party to the address specified in the heading of this Contract.

8. This Contract is drawn up in four counterparts and each party shall receive two counterparts.

9. The parties are aware of the fact that this Contract will be published in the Register of Contracts under Act no. 340/2015 Coll., on Register of Contracts because the Contracting Authority is a person obligated under this act, and the parties agree with the publication. The Contracting Authority agrees to arrange the publication within 30 days from the signature of this Contract by both parties.

10. The Contract becomes valid on the day of its signature and effective upon its publication in the Register of Contracts.

List of Annexes:

Annex no. 1: Procedure of implementing the public contract

Annex no. 2: Supplier’s Registration Certificates

| In Prague on For the Contracting Authority: ……………………………. Ing. Pavel Frelich Director of the Czech Development Agency | In ……………… on For the Supplier: .......................................................... Henok Tsegaye Tadese General Manager of HY – Engineering PLC |
| --- | --- |