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Temporary expert assignment (within the framework of transfer of Czech transitional expertise)


Title in English Language: 
European Union Support to Agriculture Competitiveness and Rural Development in Bosnia and Herzegovina (EU4AGRI)

Applicant: 
EU Delegation to Bosnia and Herzegovina 

Partner Institutions: 
United Nations Development Programme (UNDP) Bosnia and Hercegovina  

Estimated Area of Expertise: 
Strengthening institutional advisory services, enhancing information management system, policy and regulatory improvements to reinforce policy delivery in the area of Agriculture and Rural Development with focus onViticulture and Viniculture in Bosnia and Herzegovina 


Expected Start and End Dates: 
13th July – 30th September 2020 
Total Amount of Days in the Field: 
Approx. 10 days in BiH (not including the travel from Czech Republic to BiH and from BiH to Czech Republic) 
Approx,1st visit of week 20th – 26th July 2020, 2nd visit of week 31st August – 6th September 2020 

Expected Partner’s Institution Type of Cooperation: 
BiH Ministry of Foreign Trade and Economic Relations 
Ministries of Agriculture, Forestry and Water Management in Federation BiH, Republica Srpska (RS)  and Brčko Distrikt (BD) 
Agriculture Institutes and Faculties in BiH 




Context: 
Czech Development Agency (CzDA) is EU4Agri implementing partner with project coordinator UNDP. The overall objective of the Actin of EU4Agri is to modernize the agri food sector and foster rural economy in BiH. In that light, the specific objective is to increase the competitiveness of agriculture production and rural jobs and services. 
Within the Action CzDA is mainly responsible for Technical assistance component. Technical assistance will be engineered to ensure effective Grant Investment Package (GIP) management and delivery, well as to contribute to the programme objective measurable achievement. It will enable acquiring of new knowledge and skills by beneficiaries as well as advancement 
of sector-specific systems.
After meetings with entities and during programme preparation CzDA has been supported by all relevant entities to implement the action within the Viticulture and Viniculture agricultural specific sector. Technical assistance will be delivered through functional/data gap assessments, workshops, training, expert advice and data management tools. CzDA is limited with programme budget (1 400 000 Euro). 

Temporary expert scope of work within this assignment is to asses through personal meetings in BiH and collective documents and material the current situation in Viticulture and Viniculture in the areas of:
· Enhancing information management system

Expected Outcomes and Results by the Applicant:

· The agricultural statistics and the information system are not sufficiently developed to support evidence-based policy making; 
· The lack of a recent agriculture census is a major limitation in this context. Limited number of statistical indicators are produced for agriculture;
· Harmonised approach to the exchange of sectoral data across governments and their country wide consolidation, while ensuring traceability and verifiability of such data in the system, is not in place;
· Agricultural information systems must be set up in line with the EU frameworks. 


Expected time schedule:
July – desktop review of background documents 
The experts will read all relevant documents provided by the relevant stakeholders or from other sources. 

July –one week visit of BiH (planned for 20th-26th June 2020)
Component Lead with Local Coordinator will plan all meetings with relevant stakeholders to get important information and data and connection for relevant focal point person/local expert who will be available to assist Czech expert within assessment. 
The result of the visit will be all information available collected, views of expert in the country discussed, and next steps work to asses needs and suggest how project action can cover these needs.  

July-September - homebased work on assessment, regular communication with the stakeholders and Component Lead via email and skype and 
The expert will assess all relevant information and suggest the methodology how to cover the needs to cover sector within the budget. 
Expert will draft the final report composed of approx. 20 pages plus annexes. The experts will share the report and findings (proposals) with the CzDA stuff and relevant stakeholders and will regularly consult its opinions 

September – one week visit of BiH (planned for week 31th August – 6th September) and submitted final report 
Expert will conduct the second visit of BiH to complete all relevant data within the assessment and to meet all relevant people. 

The final report will be submit till 13th September. 


Expected Amount of Work in Total:
10 days in BiH (not including the travel from Czech Republic to BiH and from BiH to Czech Republic) 
30 days in Czech Republic 

Funding:
Czech Development Agency

Complementarity:	
UNDP as project coordinator 
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