AMENDMENT No. 1 TO THE CONTRACT

BETWEEN THE UNITED NATIONS DEVELOPMENT PROGRAMME (“UNDP”)

AND Ústav výzkumu globální změny AV ČR, v. v. i., UVGZ AV CR, v. v. i.  (CzechGlobe)

Reference is made to the contract number 118/12/2019, entered into on 13/12/2019 by and between the UNITED NATIONS DEVELOPMENT PROGRAMME (“UNDP”), and Ústav výzkumu globální změny AV ČR, v. v. i., UVGZ AV CR, v. v. i.  (“CzechGlobe”).

WHEREAS the contract provides that any modification thereto shall require an amendment in writing between the Parties, duly signed by the authorized representatives of UNDP and the CzechGlobe.

WHEREAS the parties have agreed to amend the contract in order to: (i) extend the date of completion of the contract; (ii) decrease contract amount; (iii) update Terms of Reference;

NOW THEREFORE, the Parties agree:

- The relevant contract provisions indicated below are hereby amended as follows:

- Article 8 of the contact is hereby amended to read as follows:

Contract Ending Date: 28/02/2021.

- Article 9 of the contact is hereby amended to read as follows:

Total Contract Amount: 109,900 USD (one hundred nine thousand nine hundred dollars)

Payment shall be made in 3 (three) instalments upon clearance of submitted deliverables:

| Deliverable | Amount and submission deadline |
| --- | --- |
| - Upon clearance of submitted phase 1 deliverables | 23,550 USD No later than 15th January 2020 |
| - Upon clearance of submitted phase 2 deliverables | 62,800 USD No later than 30th March 2020 |
| - Upon clearance of submitted phase 3 deliverables | 23,550 USD No later than 15th February 2021 |

- Updated Terms of Reference (TOR) is attached herein (extension of submission date of deliverable 3 and removal of deliverable 4).

(2)	Except as expressly modified herein in accordance with paragraph 1, all other terms of the contract shall remain unchanged and shall continue in full force and effect.

(3)	This Amendment will come into effect as of the date of last signature hereof by UNDP and the CzechGlobe.

For UNDP: 							For CzechGlobe:

By  _____________________					By  _____________________

(signature)							(signature)

Louisa Vinton				        	       		Michal V. Marek

Title: UNDP Resident Representative				Title: Director

Date: ____________________					Date: _____________________