ENCLOSURE 11 PAYMENT SCHEDULE

The terms specified in this Enclosure 11 to the Contract in capital letters, which are not expressly defined in this Enclosure 11, have the meaning assigned to them in the Contract.

This Enclosure 11 of the Contract contain Payment schedule.

| Payment milestone | Presumed due date | Amount of a partial payment of the Price for the Work |
| --- | --- | --- |
| - Signing of the Contract and hand-over of bank guarantees | 21 Days after signing the Contract | 292 975 EUR excl. VAT (5 % of the Price for the Work) (advanced payment) |
| - Purchaser’s acceptance of the Basic Design | 159 Days after signing the Contract | 585 950 EUR excl. VAT (10 % of the Price for the Work) |
| - Purchaser’s acceptance of the Detail Design | 283 Days after signing the Contract | 878 925 EUR excl. VAT (15 % of the Price for the Work) |
| - First delivery of the main components on the Site | 180 Days after receiving Purchaser’s Instruction * | 1 757 850 EUR excl. VAT (30 % of the Price for the Work) |
| - Second delivery of the main components on the Site | 240 Days after receiving Purchaser’s Instruction | 878 925 EUR excl. VAT (15 % of the Price for the Work) |
| - Provisional Acceptance of the Work | 253 Days after receiving Purchaser’s Instruction | 1 464 875 EUR excl. VAT (25 % of the Price for the Work) |
| IN TOTAL |  | 5 859 500 EUR |

Detailed payment and invoicing conditions are stated in Article 14 of the Contract.

* For the purpose of this Enclosure 11, the date of receiving the Purchaser’s Instruction anticipated by the Contractor is immediately after Purchaser’s acceptance of the Basic Design.