**Annex – Cooperation plan**

### **Name: Marek Jaskólski**

### **Period of cooperation: 1.5.2024 - 31.5.2027**

This document outlines activities in the PLUS Change project that the Ambassadors agreed to engage with. Every Ambassador have a personalized working agreement with the project, to enable them to interact in ways that best match their own expertise and interest with the needs of the project. The cooperation plan will be revised annually.

|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Nr** | **WP** | **Description** | **Format** | **Timing** | **Involvement** |
| 1  | All  | Participate in Ambassadors’ kick off   | Attendance at online meeting  | June/September 24  | x  |
| 3  | All  | Provide short video presentation of your work, and key issues you would highlight to the PLUS Change team.   | Recorded presentation  | Sometime within Aug 24 – Jan 25 (M15-M20).  | x  |
| 4  | All  | Fill your profile as ambassador to be presented to PLUS Change partners and be represented online in project channels for all followers and stakeholders (template)  | Fill template  | May 24-Sept 24 (the first month of cooperation)  | x  |
| 5  | 1  | Add key terminology relevant to your field of interest to our working glossary (i.e. if we name it, its easier to consider in our work).  | Written collaboration (via email)  | Ongoing – can be instigated whenever a word or term is identified as being important  | x  |
| 7  | 1  | Reviewing D1.1  Ethics handbook on Challenges and opportunities for just land use change. This is a practical handbook for navigating ethics, equity and justice issues in land use research and practice in Europe (EU + CH and GB)   | Written collaboration (via email)   | Shared in mid July 24 (M14)  | x  |
| 14  | 2  | Insight and discussion about the historic development in their country/region in the last 30 years  | Written contribution / online discussion   | Expected from June 24 (M13) onwards  | x  |
| 17  | 3  | Identification of policy trends that the project would otherwise overlook (and that are important to the groups the ambassadors represent).   | Written contribution / online discussion  |   | x  |
| 20  | 4  | Provide their thoughts on the past, present and future of Land Use Change, particularly the discourses around climate change and sustainability. These discourses or world views may not necessarily reflect theirs but are reflective of what is present on the ground (e.g. it could be niche/non-mainstream but there are a group of people who strongly subscribe to such world views and can permeate discussion arenas surrounding LUCC).   | Bilateral discussions/email exchanges during the development of the policy simulations.    |   | x  |
| 23  | 5  | Participate in piloting social innovations in land use policy, planning and governance in your own communities  | You can learn how policy development and piloting processes work, enhancing your advocacy skills.  |   | x  |
| 24  | 5  | Discussion/review of recommendations for policy and practice  | You can advocate for the inclusion of specific policy measures and other interventions that address the needs and challenges of your community.  |   | x  |
| 25  | 6  | Writing a blog post about your own work, and how it relates to PLUS Change  | Written contribution  | Ongoing in agreement with the communications lead  | x  |
| 27  | 6  | Identify possible speakers and contributors to conferences and policy forums  | Via email and conversation with project team  | May 26 (M36) onwards  | x  |
| 28  | 6 (T6.3)  | Signposting to policy specialists so as to maximise uptake  | email via Task lead  | Case by case from Aug 24 (M15)  | x  |
| 29  | 6 (T6.3)  | Representing PLUS Change at local events  | As per event format – in person/hybrid/online  | Case by case from Aug 24 (M15)   | x  |
| 30  | 6 (T6.3)  | Identifying and signposting participants in EU level events x2   | email via Task lead  | In line with events timetable  | x  |

Place: Place:

Date: Date:

 …………………………………………… ……………………………………………

Prof. Julia Leventon Marek Jaskólski

Scientific lead of PLUS Change project, Ambassador

Global Change Research Institute CAS