**Amendment No. 4 to the contract
Modification and Certification of the SAR Radar**

**\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_\_**

**Contractor**

|  |  |
| --- | --- |
| **Name**  | **Lake Central Air Services** |
| Registered office | 1016 Sabre Lane, Muskoka Airport, Gavenhurst ON, P1P 1R1, CANADA |
| Comp. ID No (IČ) | 1941369 | VAT | NA |
| Represented by | Yisroel Weinreb |  | CEO |

**and**

**Customer**

|  |  |
| --- | --- |
| Name | **Ústav výzkumu globální změny AV ČR, v. v. i.**(Global Change Research Institute CAS) |
| Registered office | Bělidla 986/4a, Brno, post code 603 00 |
| Comp. reg. No (IČO) | 86652079 | Tax ID No (DIČ) | CZ86652079 |
| Registered in  | Register of Public Research Institutions  |
| Represented by  | prof. RNDr. Ing. Michal V. Marek, DrSc., dr. h. c., Director |

Conclude this following Amendment:

1. **Contract**

Contracting Parties concluded on 31st of May 2023 contract for Work (as amended by Amendment No. 1 on 3th of August 2023, No. 2 on 6th of October 2023 and No. 3 on 12th of April 2024) Modification and Certification of the SAR Radar System onto a Cessna C-208 Series Caravan (hereinafter Contract).

Contracting Parties concluded on extension of deadline of fulfilment due to the followed reason:

The Contractor is waiting for the approval of the documentation by the Canadian Aviation Authority and subsequent validation by the European Aviation Authority.

1. **Changes of contract**

***Clause III. 1. of the contract changes and follows:***

1. The completed and faultless work will be handed over by 30th of June 2025.

1. **Final provisions**
	1. This Amendment may only be amended in writing in the form of numbered addenda, hereto.
	2. The Parties are aware that this Amendment meets the requirements specified in Act No 340/2015 Coll. and therefore it is subject to the obligation to be published in the register of contracts. The Contractor undertakes to enter the Amendment in the register of contracts within the statutory period and send a confirmation that the Amendment was published to the Client upon its request.
	3. This Amendment shall be elaborated in two counterparts, with each of the Contracting Parties receiving one copy thereof.
	4. This Amendment comes into force at the moment when it is published in the register of contracts.

|  |  |
| --- | --- |
| Gravenhurst on this day | Brno on this day |
|  |  |
| Yisroel Weinreb | prof. RNDr. Ing. Michal V. Marek, DrSc., dr. h. c. |
| CEO | DirectorÚstav výzkumu globální změny AV ČR, v. v. i. |
| Lake Central Air Services | (Global Change Research Institute CAS) |