|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV ZBV. |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | CHANGE REQ. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 04 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | IDENTIFICATION OF THE CONTRACT: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | CONTRACT: |  |  |  | Dated: |  |  |  |  | Purchaser: |  |  |  | S/ŘVC/062/OSP/KuP/2023 |  |  |  |  |  |  |  |  |
|  | Name of the contract: |  |  |  |  | SHIPBUILDING CONTRACT - VESSEL PRAHA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 23.04.2024 |  |  |  |  | Contractor: |  |  |  | ZMS 18-31 |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Time of Delivery by the original Contract |  |  |  |  |  |  |  |  |  |  | 23.11.2025 |  |  |  |  |  |  |
|  | Number of contract: |  |  |  |  | S/ŘVC/062/OSP/KuP/2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Time of Delivery after that change: |  |  |  |  |  |  |  |  |  |  | 21.12.2025 |  |  |  |  |  |  |
|  | Changed parts of the construction |  |  |  |  | article 5.8, 5.9, 5.10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contract parties and other subjects |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Purchaser: |  |  | Czech Republic - Waterways Directorate of the Czech Republic |  |  |  | Czech Republic, nábřeží L. Svobody 1222/12, 110 15 Praha 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Contractor: |  |  | Zeeland Maritime Services B.V. |  |  |  | The Netherlands, Zeeland Maritime Services B.V., Wemeldinge (Oostelijke Kanaalweg 20) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | INITIATOR OF THE CHANGE: |  |  |  |  | Purchaser |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CLASSIFICATION OF THE CHANGE BY § 222 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | RECAPITULATION OF THE CONTRACT PRICE INCLUDING THAT CHANGE REQUEST |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A |  |  |  | B |  |  |  | C |  |  |  | D |  |  |  | E |  |  |  |  |  | Original Contract Price: (EUR excl. VAT) |  |  |  |  |  |  |  |  |  |  |  |  | 3 300 000,00 € |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total price change - sum of all CR including this one: |  |  |  |  |  |  |  |  |  |  |  |  | 1 252 954,40 € |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Total ACTUAL price: |  |  |  |  |  |  |  |  |  |  |  |  | 4 552 954,40 € |  |  |  |  |  |  |  |  |
|  | DESCRIPTION OF THE CHANGE: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Subject of the change: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | PROPOSED CHANGES OF THE PRICE BY THAT CR |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Flowmeters for water dispensing, additional vacuum pumps for pumping out water from customers, freezing protection of bilge system tem |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Price of proposed changes NEGATIVE |  |  |  |  |  | Price of proposed changes POSITIVE |  |  |  |  |  |  | Price of proposed changes positive and negative together |  |  |  |  |  |  |  |  |
|  | Content of the change: |  |  |  |  |  |  |  |  |  |  |  |  |  | detail description in the CR Annex 1 |  |  |  |  |  |  |  | EUR excl. VAT |  |  |  | % |  | EUR excl. VAT |  |  |  |  | % |  | EUR excl. VAT |  |  |  |  |  | % |  |  |
|  | Additional flowmeters on water for customers enables correct evidence of provided service and mandatory collection of waste from vessels. 2 vacuum pumping out water from vessels of customers is necessary for pumping out from vessels of customers without their own board pumps. Freezing protection of bilge system in open ADN area on deck is necessary for provision of the collection of bilge from vessels of customers during winter period also. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | - € |  |  |  | 0,0 |  | 170 259,71 € |  |  |  |  | 5,2 |  | 170 259,71 € |  |  |  |  |  | 5,2 |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | IMPACT OF THE ACTUAL CHANGE TO THE DATE OF DELIVERY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Change of the number of days for delivery from previous CR: |  |  |  | 0 |  | Change of the number of days for delivery by this actual CR: |  |  |  |  | 28 |  | Total change of the number of days for delivery: |  |  |  |  |  | 28 |  |  |
|  | ASSESSMENT OF THE PRICE CHANGE BY §222 OF THE ACT ON THE AWARD OF PUBLIC CONTRACTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | CHANGE REQUESTS IN TOTAL: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | ACTUAL CHANGE REQUEST No: |  |  |  |  |  |  |  |  |  |  |  |  |  | 04 |  |  |  |  |  |  |  |
|  | CLASSIFICATION OF THE CHANGE BY §222: |  |  |  |  |  |  |  |  |  |  |  | LIMIT (%) |  | EUR excl. VAT |  |  |  |  |  | % |  | CLASSIFICATION OF THE CHANGE BY §222: |  |  |  |  |  |  |  |  |  |  |  | LIMIT (%) |  | EUR excl. VAT |  |  |  |  |  | % |  |
|  | B |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 10% |  | 290 942,19 Kč |  |  |  |  |  | 8,8 |  | B |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 10% |  | 0,00 Kč |  |  |  |  |  | 0,0 |  |
|  | C |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 30% |  | 962 012,21 Kč |  |  |  |  |  | 29,2 |  | C |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 30% |  | 170 259,71 Kč |  |  |  |  |  | 5,2 |  |
|  | D |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 30% |  | 0,00 Kč |  |  |  |  |  | 0,0 |  | D |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 30% |  | 0,00 Kč |  |  |  |  |  | 0,0 |  |
|  | E |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 0% |  | 0,00 Kč |  |  |  |  |  | 0,0 |  | E |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 0% |  | 0,00 Kč |  |  |  |  |  | 0,0 |  |
|  | C+D |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 30% |  | 962 012,21 Kč |  |  |  |  |  | 29,2 |  | C+D |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 30% |  | 170 259,71 Kč |  |  |  |  |  | 5,2 |  |
|  | B+C+D |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 45% |  | 1 252 954,40 Kč |  |  |  |  |  | 38,0 |  | B+C+D |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 45% |  | 170 259,71 Kč |  |  |  |  |  | 5,2 |  |
|  | B+C+D+E |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 45% |  | 1 252 954,40 Kč |  |  |  |  |  | 38,0 |  | B+C+D+E |  |  |  | Total POSITIVE and NEGATIVE changes |  |  |  |  |  |  |  | ≤ 45% |  | 170 259,71 Kč |  |  |  |  |  | 5,2 |  |
|  | Note: |  | 1) | The tables, indicating the values ​​of changes in EUR excl. and in percentages, express compliance, or possible non-compliance, with the limit values ​​set by Act 134/2016 Coll., as amended (07/2023). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | SIGNATURE OF THE CHANGE REQUEST EXPRESSES THE UNDERSIGNED'S CONSENT TO THE AMENDMENT STATEMENT IN THIS CHANGE REQUEST. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Modification is processed according to the Article 3 point a) of the CONTRACT. PURCHASER request the CONTRACTOR in writing to make modifications to the "SPECIFICATIONS". CONTRACTOR agree to carry out such modifications provided that such modifications or an accumulation of such modifications will not in the CONTRACTOR's judgment adversely affect the CONTRACTOR's planning or programme in relation to the CONTRACTOR's other commitments. By this Change Request CONTRACTOR and the PURCHASER fully agree expressly and in writing upon the (a) adjustment of price and (b) adjustment of delivery date. According to the Article 7 point d) of the CONTRACT CONTRACTOR and PURCHASER agree on a term payment in phases by Article 7 point b) of the CONTRACT. This Change Request REPLACES the amendment to the Contract, must be duly discussed with the CONTRACTOR and approved by the PURCHASER. The Change Request is deemed to be approved on the date of signature by the PURCHASER's statutory representative. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  | 2) | Assessment of changes in relation to §222: |  |  |  |  |  |  |  |  | The changes are in accordance with §222 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | The change exceeds the limit permitted by law. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Zákon 134/2016 Sb. o zadávání veřejných zakázek, §222, ve znění z 07/2023 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Popis a zdůvodnění nepředvídatelnosti, nemožnosti oddělení dodatečných prací (služeb, stavebních prací) od původní zakázky a nezbytnost změny pro dokončení předmětu původní zakázky v zatřídění dle Směrnice č.S-11/2016 o oběhu smluv a o zadávání veřejných zakázek Ředitelství vodních cest ČR v souladu s § 222 - Změna závazku ze smlouvy na veřejnou zakázku Zákona 134/2016 Sb. - Zákon o zadávání veřejných zakázek. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ZMĚNA SMLOUVY NENÍ PODSTATNOU ZMĚNOU TJ. SPADÁ POD JEDEN Z BODŮ A-E (nevztahuje se na ní odstavec 3 článku 40 Směrnice č.S-11/2016 o oběhu smluv a o zadávání veřejných zakázek Ředitelství vodních cest ČR) Verze 1.0. Při postupu podle bodu C a D nesmí celkový cenový nárůst související se změnami při odečtení stavebních prací, služeb nebo dodávek, které nebyly s ohledem na tyto změny realizovány, přesáhnout 30 % původní hodnoty závazku. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | A | Nejde o podstatnou změnu závazku, neboť změna: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | D | Nejde o podstatnou změnu závazku, neboť potřeba změny vznikla v důsledku okolností, které zadavatel jednající s náležitou péčí nemohl předvídat a tato změna nemění celkovou povahu zakázky. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (a) | by neumožnila účast jiných dodavatelů, ani nemohla ovlivnit výběr dodavatele v původním řízení; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (b) | nemění ekonomickou rovnováhu závazku ze smlouvy ve prospěch vybraného dodavatele; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | E | Za podstatnou změnu závazku ze smlouvy dle odstavce 3 na veřejnou zakázku, jejímž předmětem je provedení stavebních prací, se nepovažuje záměna jedné nebo více položek soupisu stavebních prací jednou nebo více položkami, za předpokladu že: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (c) | nevede k významnému rozšíření rozsahu plnění veřejné zakázky. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | B | Nejde o podstatnou změnu závazku, neboť finanční limit změny (a souhrn všech předpokládaných změn smlouvy) je nižší než 15 % původní hodnoty závazku ze Smlouvy na veřejnou zakázku na stavební práce (10 % u ostatních zakázek). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (a) | nové položky soupisu stavebních prací představují srovnatelný druh materiálu nebo prací ve vztahu k nahrazovaným položkám; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | C | Nejde o podstatnou změnu závazku, neboť dodatečné stavební práce /služby od dodavatele původní veřejné zakázky jsou nezbytné |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (b) | cena materiálu nebo prací podle nových položek soupisu stavebních prací je ve vztahu k nahrazovaným položkám stejná nebo nižší; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (c) | materiál nebo práce podle nových položek soupisu stavebních prací jsou ve vztahu k nahrazovaným položkám kvalitativně stejné nebo vyšší; |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Cílem provozu servisní lodě v centru Prahy je kontinuální poskytování servisních služeb v maximální úrovni kvality. Je tak nezbytné doplnit řešení měření a evidence odebraných i vydaných vod, rozšíření služby odčerpávání vakuovým čerpadlem ze dna plavidel a ochrana čerpadla nádních vod proti mrazu pro poskytování služby i během zimního období. Dodatečné požadavky vyplynuly z upřesnění funkčních nároků plavidla a zapracováním zkušeností z dalších servisních center. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | a změna v osobě dodavatele: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (a) | není možná z ekonomických nebo technických důvodů |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Technické důvody představuje potřeba dodání v integrovaném provedení s dalšími palubními systémy, což prostřednictvím jiného dodavatele jiné technologie, která nemusí být plně kompatibilní, nezajistí spolehlivě funkční řešení. Současně dodatečnou montáží jiným dodavatelem by došlo k narušení protikorozních ochran trupu plavidla i palubních systémů. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (b) | by zadavateli způsobila značné obtíže nebo výrazné zvýšení nákladů |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Plavidlo dodavatel dodává s klasifikačním průkazem a zárukou funkčnosti jako celku. Při realizaci části doplňkových čerpadel či měřících zařízení nebo elektrických zařízení jiným dodavatelem by nebyla garantována funkčnost a za soulad integrace s předpisy by zodpovídal objednatel, nikoliv dodavatel. Současně by bylo nutné provedení opětovné klasifikační prohlídky a nového klasifikačního průkazu, vyžadujícího dodatečné náklady. Jedná se o nepřiměřenou míru rizik, která není kompenzována případnou jednorázovou úsporou pořizovacích nákladů. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | (d) | zadavatel vyhotoví o každé jednotlivé záměně přehled obsahující nové položky soupisu stavebních prací s vymezením položek v původním soupisu stavebních prací, které jsou takto nahrazovány, spolu s podrobným a srozumitelným odůvodněním srovnatelnosti materiálu nebo prací podle písmene a) a stejné nebo vyšší kvality podle písmene c). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | STATEMENTS, SIGNATURES: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Zhotovitel: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Name Position |  |  |  |  |  |  |  | Date: |  |  |  |  |  | Signature: |  |  |  |  |  |  |  |  |  |  |  |
|  | Zeeland Maritime Services B.V. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | xxxx |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Objednatel: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Czech Republic - Waterways Directorate of the Czech Republic |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Vedoucí oddělení garanta smlouvy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Name Position |  |  |  |  |  |  |  | Date: |  |  |  |  |  | Signature: |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | xxxx |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Manager OSP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Odd. vnitř. správy, správce rozpočtu |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Name Position |  |  |  |  |  |  |  | Date: |  |  |  |  |  | Signature: |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | xxxx |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Manager OVS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Statutory representative, Objednatel, Příkazce operace |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Name Position |  |  |  |  |  |  |  | Date: 14.11.2025 |  |  |  |  |  | Signature: |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Ing. Lubomír Fojtů |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Director |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | ANNEXES (1+2) AND OTHER RELATED DOCUMENTS OF THE CHANGE REQUEST: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1 | Detailed description and justification of changes |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 5 |  |  |  |  |  |  |  |  |  |  |  |  |  | 9 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2 | Recapitulation of the costs of the Change request by individual sections affected by the change, broken down according to § 222 of the Act |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 6 |  |  |  |  |  |  |  |  |  |  |  |  |  | 10 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3 | Annex to the PRAHA contract - technical description and calculation by the Contractor |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 7 |  |  |  |  |  |  |  |  |  |  |  |  |  | 11 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 8 |  |  |  |  |  |  |  |  |  |  |  |  |  | 12 |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SHIPBUILDING CONTRACT - VESSEL PRAHA |  |  |  |  | CHANGE REQUEST |  |  |  |  |  |  |  |  | No: |  | 04 |  |  |  |  | ANNEX 1 OF THE CHANGE REQUEST |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | DETAILED DESCRIPTION AND JUSTIFICATION OF CHANGES |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1) |  | Subject: |  |  |  |  |  | Flowmeters for water dispensing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Classification: |  |  |  |  |  |  | C |  |  |  |
|  |  |  | 3 x flowmeter (water / bilge / black water) for dispensing to customers (in chapter 5.8 a 5.9 are specified only hoses but not measurement for selling of services) that enables correct evidence for both selling of service and evidence for vessels about mandatory collection of waste. The flowmeters are approved to be located in the loading-zone and are equipped with a Modbus communication interface to be able to read through the BergMM measuring-system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2) |  | Subject: |  |  |  |  |  | Pumps for pumping out water from customers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Classification: |  |  |  |  |  |  | C |  |  |  |
|  |  |  | 2 vacuum pumps for pumping out water from vessels of customers (in chapter 5.9 are specified pumps for discharging vessel tanks to shore only). For vessels of customers without their own board pumps it is necessary to have a vacuum pump on bunker vessel for entire pumping out of bottom and waste water. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 3) |  | Subject: |  |  |  |  |  | Freezing protection of bilge system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Classification: |  |  |  |  |  |  | C |  |  |  |
|  |  |  | Tracing / insulation against freezing of the bilge pump and measurement unit on deck that needs to be in the ADN area (outside the covered deck), including necessary cables and control system. Service of bilge pump needs to be provided in winter period also, therefore drying of the system for freezing protection is not appropriate to the higher level of provided continuous service to customers. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 4) |  | Subject: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Classification: |  |  |  |  |  |  |  |  |  |  |
|  | 5) |  | Subject: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Classification: |  |  |  |  |  |  |  |  |  |  |
|  | 6) |  | Subject: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Classification: |  |  |  |  |  |  |  |  |  |  |
|  | SHIPBUILDING CONTRACT - VESSEL PRAHA |  |  |  |  |  | CHANGE REQUEST |  |  |  |  |  |  |  | No: |  | 04 |  |  |  |  | ANNEX 2 OF THE CHANGE REQUEST |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | SUMMARY OF THE COSTS OF THE CHANGE REQUEST IN BREAKDOWN ACCORDING TO §222 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Affected part |  |  |  |  | Section |  |  |  |  |  |  | B |  |  |  |  |  |  |  | C |  |  |  |  |  |  |  | D |  |  |  |  |  |  |  | E |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | POSITIVE |  |  |  | NEGATIVE |  |  |  | POSITIVE |  |  |  | NEGATIVE |  |  |  | POSITIVE |  |  |  | NEGATIVE |  |  |  | POSITIVE |  |  |  | NEGATIVE |  |  |  |
|  | No: | art. 5.8, 5.9 |  |  |  | 3 x flowmeter |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 73 342,50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Development functionalities |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 19 238,84 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Flowmeters for water dispensing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EUR for part in total: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (B+C+D+E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | positive |  | 92 581,34 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | negative |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | total |  | 92 581,34 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | No: | article 5.9 |  |  |  | 2 vacuum pumps |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 56 310,87 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Pumps for pumping out water from customers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EUR for part in total: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (B+C+D+E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | positive |  | 56 310,87 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | negative |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | total |  | 56 310,87 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | No: | article 5.10 |  |  |  | Tracing / insulation against freezing |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 21 367,50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Freezing protection of bilge system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EUR for part in total: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (B+C+D+E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | positive |  | 21 367,50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | negative |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | total |  | 21 367,50 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EUR for part in total: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (B+C+D+E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | positive |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | negative |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | total |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EUR for part in total: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (B+C+D+E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | positive |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | negative |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | total |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | No: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Name: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | EUR for part in total: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | (B+C+D+E) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | positive |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | negative |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | total |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | B+ |  |  |  | B- |  |  |  | C+ |  |  |  | C- |  |  |  | D+ |  |  |  | D- |  |  |  | E+ |  |  |  | E- |  |  |  |
|  |  |  |  |  |  | TOTAL EUR excl. VAT |  |  |  |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 170 259,71 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  |
|  |  |  |  |  |  | VAT 0% |  |  |  |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 35 754,54 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  |
|  |  |  |  |  |  | TOTAL EUR incl. VAT |  |  |  |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 206 014,24 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  |
|  |  |  |  |  |  | CHANGE REQUEST TOTAL: |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | B + C + D + E |  |  |  |  |  |  | EUR excl. VAT |  |  |  | VAT 0% |  |  |  | EUR incl. VAT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Changes positive total: |  |  |  |  |  |  | 170 259,71 |  |  |  | 35 754,54 |  |  |  | 206 014,24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Changes negative total: |  |  |  |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  | 0,00 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  | Changes positive and negative |  |  |  |  |  |  | 170 259,71 |  |  |  | 35 754,54 |  |  |  | 206 014,24 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |