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CONSORTIUM AGREEMENT
THIS CONSORTIUM AGREEMENT is based upon Regulation (EU) No 2021/695 of the European Parliament and of the Council of 28 April 2021 establishing Horizon Europe – the Framework Programme for Research and Innovation (2021-2027), laying down its rules for participation and dissemination (hereinafter referred to as “Horizon Europe Regulation”), and on the European Commission’s General Model Grant Agreement and its Annexes, and is made on 01.01.2026 hereinafter referred to as the Effective Date
BETWEEN:
1. UNIVERZITA KARLOVA (CUNI), established in OVOCNY TRH 560/5, PRAHA 1, 11636, Czech Republic, VAT number CZ00216208, the Coordinator
hereinafter jointly referred to as Beneficiaries
2. NARODNI KNIHOVNA CESKE REPUBLIKY (NKP), PIC 999623510, established in KLEMENTINUM 190, PRAHA 1 110 01, Czechia, 
3. THE CHANCELLOR MASTERS AND SCHOLARS OF THE UNIVERSITY OF CAMBRIDGE (UCAM), PIC 999977172, established in TRINITY LANE THE OLD SCHOOLS, CAMBRIDGE CB2 1TN, United Kingdom, 
4. THE CHANCELLOR, MASTERS AND SCHOLARS OF THE UNIVERSITY OF OXFORD (UOx), PIC 999984350, established in WELLINGTON SQUARE UNIVERSITY OFFICES, OXFORD OX1 2JD, United Kingdom, 
5. QUEEN MARY UNIVERSITY OF LONDON (QMUL), PIC 999847677, established in 327 MILE END ROAD, LONDON E1 4NS, United Kingdom, 
6. OESTERREICHISCHE AKADEMIE DER WISSENSCHAFTEN (OEAW), PIC 999823912, established in DR. IGNAZ SEIPEL-PLATZ 2, WIEN 1010, Austria, 
7. UNIVERSITA DEGLI STUDI DI FIRENZE (UNIFI), PIC 999895789, established in Piazza San Marco 4, Florence 50121, Italy,
8. RUPRECHT-KARLS-UNIVERSITAET HEIDELBERG (UHEI), PIC 999987648, established in SEMINARSTRASSE 2, HEIDELBERG 69117, Germany, 
9. UNIVERSITY OF HAMBURG (UHAM), PIC 999905101, established in MITTELWEG 177, HAMBURG 20148, Germany, 
10. UNIWERSYTET WROCLAWSKI (UWr), PIC 999845155, established in PL UNIWERSYTECKI 1, WROCLAW 50137, Poland, 
11. UNIWERSYTET WARSZAWSKI (UWar), PIC 999572294, established in KRAKOWSKIE PRZEDMIESCIE 26/28, WARSZAWA 00-927, Poland, 
12. CHORHERRENSTIFT KLOSTERNEUBURG (KLN), PIC 874088244, established in STIFTSPLATZ 1, KLOSTERNEUBURG 3400, Austria,
relating to the Action entitled
Papyri and Manuscripts: Exploring Layers of Ages, in short PAMELA hereinafter referred to as “Project”
WHEREAS:
The Parties, having considerable experience in the field concerned, have submitted a proposal for the Project to the Granting Authority as part of Horizon Europe – the Framework Programme for Research and Innovation (2021-2027).
The Parties wish to specify or supplement binding commitments among themselves in addition to the provisions of the specific Grant Agreement to be signed by the Beneficiaries and the Granting Authority (hereinafter “Grant Agreement”).
The Parties are aware that this Consortium Agreement is based upon the DESCA model consortium agreement.
NOW, THEREFORE, IT IS HEREBY AGREED AS FOLLOWS:
[bookmark: _Toc90629805][bookmark: _Toc221176491]Definitions
Definitions
Words beginning with a capital letter shall have the meaning defined either herein or in the Horizon Europe Regulation or in the Grant Agreement including its Annexes.
Additional Definitions
[bookmark: _Hlk136501845]‘Associated Partner’ means any legal entities listed as Associated Partner in Art. 9.1 of the Grant Agreement which participate in the action, but without the right to charge costs or claim contributions from the Granting Authority. APs have to comply with the contractual provisions of this Consortium Agreement in the same way as the Beneficiaries unless stated otherwise in this Consortium Agreement. An AP can provide additional training and may host Fellows during Secondments. An AP shall enter into a separate agreement with the Coordinator or the Party employing the Fellow.
“Consortium Body”
Consortium Body means any management body described in Section 6 (Governance Structure) of this Consortium Agreement.
“Consortium Plan”
Consortium Plan means the description of the Action and the related agreed budget as first defined in the Grant Agreement and which may be updated by the Steering Committee.
“Defaulting Party”
Defaulting Party means a Party which the Steering Committee has declared to be in breach of this Consortium Agreement and/or the Grant Agreement as specified in Section 4.3 of this Consortium Agreement.
[bookmark: _Hlk136502277]“Granting Authority” 
[bookmark: _Hlk136502349]Granting Authority means the European Union body awarding the grant for the Project.
“Marie Skłodowska-Curie Fellow” or “Fellow” 
Marie Skłodowska-Curie Fellow or Fellow means a recruited Staff funded within the scheme of this MSCA Staff Exchanges (SE).
“Needed”
Needed means:
For the implementation of the Project:
Access Rights are Needed if, without the grant of such Access Rights, carrying out the tasks assigned to the recipient Party would be technically or legally impossible, significantly delayed, or require significant additional financial or human resources.
For Exploitation of own Results:
Access Rights are Needed if, without the grant of such Access Rights, the Exploitation of own Results would be technically or legally impossible.
“Secondment” 
Secondment means a period during which a Fellow is hosted by a Party or a Associated Partner other than his/her employing entity. 
“Software”
Software means sequences of instructions to carry out a process in, or convertible into, a form executable by a computer and fixed in any tangible medium of expression.
“Staff” 
Staff means any employee from one of the Parties. 
[bookmark: _Toc90280821][bookmark: _Toc90286075][bookmark: _Toc90286097][bookmark: _Toc90241045][bookmark: _Toc90280822][bookmark: _Toc90286076][bookmark: _Toc90286098][bookmark: _Toc90629806][bookmark: _Toc221176492]Purpose
The purpose of this Consortium Agreement is to specify with respect to the Project the relationship among the Parties, in particular concerning the organisation of the work between the Parties, the management of the Project and the rights and obligations of the Parties concerning inter alia liability, Access Rights and dispute resolution. In case of inconsistencies between this Consortium Agreement and this Grant Agreement, the Grant Agreement and its annexes shall prevail.
[bookmark: _Toc90241047][bookmark: _Toc90280824][bookmark: _Toc90241048][bookmark: _Toc90280825][bookmark: _Toc90629807][bookmark: _Toc221176493]Entry into force, duration and termination
Entry into force
An entity becomes a Party to this Consortium Agreement upon signature of this Consortium Agreement by a duly authorised representative.
This Consortium Agreement shall have effect from the Effective Date identified at the beginning of this Consortium Agreement.
An entity becomes a new Party to the Consortium Agreement upon signature of the accession document (Attachment 2) by the new Party and the Coordinator. Such accession shall have effect from the date identified in the accession document.
[bookmark: _Toc90241051]Duration and termination
This Consortium Agreement shall continue in full force and effect until complete fulfilment of all obligations undertaken by the Parties under the Grant Agreement and under this Consortium Agreement.
However, this Consortium Agreement or the participation of one or more Parties to it may be terminated in accordance with the terms of this Consortium Agreement.
If
the Grant Agreement is not signed by the Granting Authority or a Beneficiary, or 
the Grant Agreement is terminated, or
a Beneficiary’s participation in the Grant Agreement is terminated, 
this Consortium Agreement shall automatically terminate in respect of the affected Party/ies, subject to the provisions surviving the expiration or termination under Section 3.3 of this Consortium Agreement. 
If an Associated Partner´s participation in the Project is terminated, its participation in this Consortium Agreement may be terminated subject to the provisions surviving the expiration or termination under this Consortium Agreement (Section 4.2 and Section 3.3).
[bookmark: _Toc90241053][bookmark: _Toc90241054][bookmark: _Ref90241180]Survival of rights and obligations
The provisions relating to Access Rights, Dissemination and confidentiality, for the time period mentioned therein, as well as for liability, applicable law and settlement of disputes shall survive the expiration or termination of this Consortium Agreement.
Termination shall not affect any rights or obligations of a Party leaving the Project incurred prior to the date of termination, unless otherwise agreed between the Steering Committee and the leaving Party. This includes the obligation to provide all necessary input, deliverables and documents for the period of its participation.
[bookmark: _Toc90241056][bookmark: _Toc90280827][bookmark: _Toc90629808][bookmark: _Toc221176494]Responsibilities of Parties
General principles
Each Party undertakes to take part in the efficient implementation of the Project, and to cooperate, perform and fulfil, promptly and on time, all of its obligations under the Grant Agreement and this Consortium Agreement as may be reasonably required from it and in a manner of good faith as prescribed by Belgian law.
Each Party undertakes to notify promptly the Granting Authority and the other Parties, in accordance with the governance structure of the Project, of any significant information, fact, problem or delay likely to affect the Project.
Each Party shall promptly provide all information reasonably required by a Consortium Body or by the Coordinator to carry out its tasks and shall responsibly manage the access of its employees to the EU Funding & Tenders Portal.
[bookmark: _Ref90241178][bookmark: _Ref90241179][bookmark: _Ref90241247][bookmark: _Ref90241513][bookmark: _Ref90241734]Each Party shall take reasonable measures to ensure the accuracy of any information or materials it supplies to the other Parties.
4.3 Specific obligations with regard to the Fellow (s)
Each Party that selects and recruits a Fellow to participate in the Project must respect the recruitment and working conditions for Fellows in particular the rules in the Specific Rules for Carrying out the Action in Annex 5 of the Grant Agreement.
4.4 Obligations during Secondments 
[bookmark: _Hlk136505292]During any period of Secondment to a Party or an Associated Partner, the seconded Fellow shall remain employed by the Party by which he/she was recruited.  
[bookmark: _Hlk136505327]Except as otherwise set out in this Section 4.4, the Party employing the Fellow shall be solely responsible for the fulfillment towards its Fellow of the obligations of Parties set out in in Annex 5 of the Grant Agreement, including the distribution to the Fellow of the monthly support in accordance with the Party’s own usual accounting and management principles and practices. 
[bookmark: _Hlk136505443]Except as otherwise set out in this Section 4.4, the Party hosting the Fellow shall have no obligation or liability to the employing Party or to the Fellow for any of the conditions set out in in Annex 5 of the Grant Agreement, including but not limited to liability to the Employing Party or to the Fellow for any salary or other compensation or other benefits of employment, such as any medical or other insurance coverage. 
The Party hosting the Fellow shall communicate to and instruct the Fellow in any applicable local procedures regarding, but not limited to, health and safety and proper scientific conduct to ensure that the seconded Fellow enjoys at the place of Secondment at least the same standards and working conditions as those applicable to local persons holding a similar position.
Beneficiary collaborating with an Associated Partner shall 
· Ensure to have a written commitment in place,
· enter into an Agreement with the Associated Partner with respect to any Secondment before the Secondment takes place,
· Inform the Coordinator about any Partnership Agreement agreed upon.
4.5. Fellow (Recruitment and Secondment) notifications
In order to facilitate the monitoring activity of the Coordinator, the Parties commit to notify the Coordinator via e-mail, without unnecessary delay, 
· about any progress or change in their Fellow recruitment process. In particular, the Coordinator shall always be notified about the official start date of the recruitment and the submission of the researcher declaration through the European Commission Participant Portal as well as any circumstances possibly leading to an amendment suspending (part of the) grant or prolonging the duration of the Action;
· about any major change of the planned Secondment(s).
4.6 Breach
In the event that the Steering Committee identifies a breach by a Party of its obligations under this Consortium Agreement or the Grant Agreement (e.g. improper implementation of the Project), the Coordinator or, if the Coordinator is in breach of its obligations, the Party appointed by the Steering Committee, will give formal notice to such Party requiring that such breach will be remedied within 30 calendar days from the date of receipt of the written notice by the Party.
If such breach is substantial and is not remedied within that period or is not capable of remedy, the Steering Committee may decide to declare the Party to be a Defaulting Party and to decide on the consequences thereof which may include termination of its participation.
[bookmark: _Toc90241060]4.7 Involvement of third parties
A Party that enters into a subcontract or otherwise involves third parties (including but not limited to Affiliated Entities or other Participants) in the Project remains responsible for carrying out its relevant part of the Project and for such third party’s compliance with the provisions of this Consortium Agreement and of the Grant Agreement. Such Party has to ensure that the involvement of third parties does not affect the rights and obligations of the other Parties under this Consortium Agreement and the Grant Agreement.
[bookmark: _Toc90241062]4.8 Specific responsibilities regarding data protection
Where necessary, the Parties shall cooperate in order to enable one another to fulfil legal obligations arising under applicable data protection laws (the Regulation (EU) 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regard to the processing of personal data and on the free movement of such data and relevant national data protection law applicable to said Party) within the scope of the performance and administration of the Project and of this Consortium Agreement.
In particular, the Parties shall, where necessary, conclude a separate data processing, data sharing and/or joint controller agreement before any data processing or data sharing takes place.
[bookmark: _Toc90241064][bookmark: _Toc90280829][bookmark: _Toc90241065][bookmark: _Toc90280830][bookmark: _Toc90629809][bookmark: _Toc221176495]Liability towards each other
No warranties
In respect of any information or materials (incl. Results and Background) supplied by one Party to another under the Project, no warranty or representation of any kind is made, given or implied as to the sufficiency or fitness for purpose nor as to the absence of any infringement of any proprietary rights of third parties.
Therefore,
the recipient Party shall in all cases be entirely and solely liable for the use to which it puts such information and materials, and
no Party granting Access Rights shall be liable in case of infringement of proprietary rights of a third party resulting from any other Party (or its entities under the same control) exercising its Access Rights.
[bookmark: _Ref90241337]Limitations of contractual liability
No Party shall be responsible to any other Party for any indirect or consequential loss or similar damage such as, but not limited to, loss of profit, loss of revenue or loss of contracts, provided such damage was not caused by a wilful act.
A Party’s general aggregate liability towards the other Parties collectively shall be limited to once the Party’s share of the total costs of the Project as identified in Annex 2 of the Grant Agreement. 
A Party’s liability shall not be limited under either of the two foregoing paragraphs to the extent such damage was caused by a wilful act or gross negligence or to the extent that such limitation is not permitted by law.
[bookmark: _Toc90241069][bookmark: _Toc90241070]Damage caused to third parties
Each Party shall be solely liable for any loss, damage or injury to third parties resulting from the performance of the said Party’s obligations by it or on its behalf under this Consortium Agreement or from its use of Results or Background.
[bookmark: _Toc90241072]Force Majeure
No Party shall be considered to be in breach of this Consortium Agreement if it is prevented from fulfilling its obligations under the Consortium Agreement by Force Majeure.
Each Party will notify the Steering Committee of any Force Majeure without undue delay. If the consequences of Force Majeure for the Project are not overcome within 6 weeks after such notice, the transfer of tasks - if any - shall be decided by the Steering Committee.
[bookmark: _Ref90240509][bookmark: _Toc90629810][bookmark: _Toc221176496]Governance structure
General structure
The organisational structure of the consortium shall comprise the following Consortium Bodies:
The Steering Committee is the decision-making body of the consortium.
The Coordinator is the legal entity acting as the intermediary between the Parties and the Granting Authority. The Coordinator shall, in addition to its responsibilities as a Party, perform the tasks assigned to it as described in the Grant Agreement and this Consortium Agreement. 
[bookmark: _Toc90241076]Steering Committee
The Steering Committee shall consist of one representative of each Party (hereinafter referred to as “Scientific 1”) as listed in the section 6.2.1 of this Consortium Agreement.
The Steering Committee must provide required information in a timely manner to the Coordinator. Parties are responsible for replacing contacts promptly in case of absence, ensuring that all project-related communications and reporting obligations can be fulfilled without delay. The Steering Committee is responsible for supporting the Coordinator in the preparation of reports, interim payments, and any other obligations arising from the Grant Agreement.
The Steering Committee provides recommendations on project implementation, progress evaluation, and planning of further activities. The following decisions shall be taken by the Steering Committee:
· Proposals for changes to Annexes 1 and 2 of the Grant Agreement to be agreed by the Granting Authority
· Changes to the Consortium Plan 
· Entry of a new Party to the Project and approval of the settlement on the conditions of the accession of such a new Party
· Withdrawal of a Party from the Project and the approval of the settlement on the conditions of the withdrawal
· Proposal to the Granting Authority for a change of the Coordinator
· Proposal to the Granting Authority for suspension of all or part of the Project
· Proposal to the Granting Authority for termination of the Project and the Consortium Agreement
· Identification of a breach by a Party of its obligations under this Consortium Agreement or the Grant Agreement 
· Declaration of a Party to be a Defaulting Party 
· Remedies to be performed by a Defaulting Party
· Termination of a Defaulting Party’s participation in the consortium and measures relating thereto 
· Steps to be taken for litigation purposes and the coverage of litigation costs in case of joint claims of the parties of the consortium against a Party 

The Steering Committee shall meet online at least once every six months. Any member may request an extraordinary meeting if necessary. The Coordinator is responsible for organising and chairing meetings of the Steering Committee.
Meeting outcomes and recommendations shall be documented and circulated to all beneficiaries, ensuring transparency. The Coordinator shall circulate draft minutes to all beneficiaries within seven (7) calendar days after the meeting. The minutes shall be deemed approved unless objections are raised within five (5) working days of circulation. All records shall be retained by the Coordinator for the duration of the project and at least five (5) years after its end.
Each Party has one vote. The Steering Committee is quorate if more than half of the Parties are represented, either in person or by delegation. Recommendations are adopted by a simple majority of votes of those present or represented. Any decision may also be taken without a meeting if
a) the Coordinator circulates to all Members of the Steering Committee a suggested decision 	with a deadline for responses of at least 10 calendar days after receipt by a Party and
b) the decision is agreed by a simple majority of all Parties.
The Coordinator shall inform all the Members of the outcome of the vote.
[bookmark: _Int_wmQsSR57]Each member may delegate their participation or vote to another colleague from their institution or to another Beneficiary representative, provided written notice is given to the Coordinator at least 24 hours prior to the meeting.
Members of the Steering Committee shall act in the best interest of the Consortium as a whole. They shall avoid conflicts of interest and maintain the confidentiality of discussions and materials, unless otherwise agreed in writing.
Recommendations of the Steering Committee do not override the Coordinator’s responsibility for project implementation, reporting, or financial decisions.
6.2.1 Contacts
Each Party is responsible for nominating two scientific contacts and one administrative contact. Nominated contacts must be available to provide required information in a timely manner to the Coordinator. Contacts are responsible for relaying the Steering Committee’s recommendations and for supporting the Coordinator in the preparation of reports, interim payments, and any other obligations arising from the Grant Agreement. In the event of any change in designated contacts, the Party shall promptly notify the Coordinator.  Such changes do not require an amendment to the Consortium Agreement.

The nominated contacts are:

1. UNIVERZITA KARLOVA (CUNI), established in OVOCNY TRH 560/5, PRAHA 1, 11636, Czech Republic, VAT number CZ00216208
Scientific 1:	X
Scientific 2:	X
Administrative: 	X

2. NARODNI KNIHOVNA CESKE REPUBLIKY (NKP), PIC 999623510, established in KLEMENTINUM 190, PRAHA 1 110 01, Czechia, 
Scientific 1:	X
Scientific 2:	X
Administrative: X

3. THE CHANCELLOR MASTERS AND SCHOLARS OF THE UNIVERSITY OF CAMBRIDGE (UCAM), PIC 999977172, established in TRINITY LANE THE OLD SCHOOLS, CAMBRIDGE CB2 1TN, United Kingdom, 
Scientific 1:	X
Scientific 2:	X
Administrative:	X
X 

4. THE CHANCELLOR, MASTERS AND SCHOLARS OF THE UNIVERSITY OF OXFORD (UOx), PIC 999984350, established in WELLINGTON SQUARE UNIVERSITY OFFICES, OXFORD OX1 2JD, United Kingdom, 
Scientific 1:        X
X 
Scientific 2:  	X
X
Administrative: 	X

5. QUEEN MARY UNIVERSITY OF LONDON (QMUL), PIC 999847677, established in 327 MILE END ROAD, LONDON E1 4NS, United Kingdom, 
Scientific 1:	X 
Scientific 2:     	X 
Administrative:  X 

6. OESTERREICHISCHE AKADEMIE DER WISSENSCHAFTEN (OEAW), PIC 999823912, established in DR. IGNAZ SEIPEL-PLATZ 2, WIEN 1010, Austria, 
Scientific 1: 	X
Scientific 2: 	X
Administrative: 	X

7. UNIVERSITA DEGLI STUDI DI FIRENZE (UNIFI), PIC 999895789, established in Piazza San Marco 4, Florence 50121, Italy,
Scientific 1:	X
Scientific 2: 	X
Administrative:	X

8. RUPRECHT-KARLS-UNIVERSITAET HEIDELBERG (UHEI), PIC 999987648, established in SEMINARSTRASSE 2, HEIDELBERG 69117, Germany, 
Scientific 1:	X
Scientific 2:	X
Administrative: X

9. UNIVERSITY OF HAMBURG (UHAM), PIC 999905101, established in MITTELWEG 177, HAMBURG 20148, Germany, 
Scientific 1:	X
Scientific 2:	X
Administrative: 	X

10. UNIWERSYTET WROCLAWSKI (UWr), PIC 999845155, established in PL UNIWERSYTECKI 1, WROCLAW 50137, Poland, 
Scientific 1:	X
Scientific 2:	X
Administrative:	X

11. UNIWERSYTET WARSZAWSKI (UWar), PIC 999572294, established in KRAKOWSKIE PRZEDMIESCIE 26/28, WARSZAWA 00-927, Poland, 
[bookmark: _Hlk213756962]Scientific 1:	X
Scientific 2:	X
Administrative:	X

12. CHORHERRENSTIFT KLOSTERNEUBURG (KLN), PIC 874088244, established in STIFTSPLATZ 1, KLOSTERNEUBURG 3400, Austria,
Scientific 1:	X 
Scientific 2:	X
Administrative:	X

Coordinator
6.3.1	 
The Coordinator shall be the intermediary between the Parties and the Granting Authority and shall perform all tasks assigned to it as described in the Grant Agreement and in this Consortium Agreement.
6.3.2	 
In particular, the Coordinator shall be responsible for:
· monitoring compliance by the Parties with their obligations under this Consortium Agreement and the Grant Agreement
· keeping the address list of Members and other contact persons updated and available
· collecting, reviewing to verify consistency and submitting reports, other deliverables (including financial statements and related certification) and specific requested documents to the Granting Authority
· preparing the meetings, proposing decisions and preparing the agenda of Steering Committee meetings, chairing the meetings, preparing the minutes of the meetings and monitoring the implementation of decisions taken at meetings
· transmitting promptly documents and information connected with the Project to any other Party concerned
· administering the financial contribution of the Granting Authority and fulfilling the financial tasks described in Section 7.2
· providing, upon request, the Parties with official copies or originals of documents that are in the sole possession of the Coordinator when such copies or originals are necessary for the Parties to present claims
· providing a copy of the signed Grant Agreement, its Annexes and information on any amendments to the Associated Partners.
· If one or more of the Parties is late in submission of any Project deliverable, the Coordinator may nevertheless submit the other Parties’ Project deliverables and all other documents required by the Grant Agreement to the Granting Authority in time.
6.3.3	 
If the Coordinator fails in its coordination tasks, the Steering Committee may propose to the Granting Authority to change the Coordinator.
6.3.4	 
The Coordinator shall not be entitled to act or to make legally binding declarations on behalf of any other Party or of the consortium, unless explicitly stated otherwise in the Grant Agreement or this Consortium Agreement.
6.3.5	 
The Coordinator shall not enlarge its role beyond the tasks specified in this Consortium Agreement and in the Grant Agreement.
[bookmark: _Toc221176497]Project implementation and Division of Tasks
Internal reporting

Each Party remains solely responsible for the accuracy and completeness of these reports and for ensuring that all information and documents are available to the Funding Authority in case of audit or review, in accordance with the Grant Agreement. 
The Coordinator shall not be held liable for any inaccuracy or omission in the reports submitted by the Parties.
Division of Tasks
Responsibilities are according to the Grant Agreement. Additional responsibilities are specified in sections 7.2.1. and 7.2.2.
Deliverables
While the Grant Agreement specifies only the leading institution for each deliverable, this Consortium agreement adds further institutions that will substantially contribute to producing the deliverables in accordance with the timelines and quality standards agreed within the Consortium.
Leading institutions remain solely responsible for the timely submission and overall quality of each deliverable to the Funding Authority. Contributing Parties shall, however, cooperate with the leading institution and the Consortium in case of audits or reviews by the Funding Authority, and shall retain documentation of their contributions for internal record-keeping purposes. Each contributing Party remains fully responsible for the accuracy and completeness of the information it provides.
WP1
D1.1 (M06) Data Management Plan 
NKP, CU, all
D1.2 (M48) Report on new methods in preservation and research of papyri 
UOx, UHEI, UWar
D1.3 (M45) Online papyri digitization edition analysis and open access joint publications
UHEI, UNIFI, UWar, NKP
D1.4 (M45) Wessely papyrus collection exhibition 
NKP, CU, UHEI
WP2
D2.1 (M48) Database of medieval scribes and colophons 
CU, NKP, UWr, KLN, OEAW
D2.2 (M06) Prague exhibition on medieval scribes
	CU, NKP, UHEI
WP3
D3.1 (M45) Report on efficiency and good practice in virtual re-creation of medieval manuscript collections and other research publications 
OEAW, Uwr, NKP, CU
D3.2 (M48) Publications on cutting-edge methodologies in manuscript research and other research publications 
QMUL, UHAM, NKP, CU
D3.3 (M24) Exhibition on late medieval manuscripts from the convent of St Catharine
	StGall, CU, KLN, OEAW
D3.4 (M36) Klosterneuburg manuscript exhibition
	KLN, CU,
WP4
D4.1 (M13) Progress report 
CU, all
D4.2 (M18) Mid-term meeting 
CU, KLN, all
D5.1 (M06) Plan for dissemination and exploitation including communication activities 
NKP, CU, all
Summer schools and trainings
The Beneficiaries agree to take responsibility for organizing and implementing the following trainings (also listed in the Grant Agreement), as well as activities listed below under 8.1.3 B1:
WP1
S1.1 Greek Papyrology I 			– NKP (M09)
S1.2 Greek Papyrology II 			– UHEI, NKP (M21)
S1.3 Greek Papyrology III 			– NKP (M33)
S1.4 Greek Papyrology IV 			– NKP (M45)
S1.5 Papyri conservation workshop I		– UOx (M17–18)
S1.6 Papyri conservation workshop II 		– UOx (M41–42)

WP2
S2.1 Cambridge <Hands:On> Hackathon I 	– UCam (M06 or M07) 
S2.2 Cambridge <Hands:On> Hackathon IV	– UCam (M42 or M43)

WP3
S3.1 Cambridge <Hands:On> Hackathon II	– UCam (M18 or M19)
S3.2 Cambridge <Hands:On> Hackathon III	– UCam (M30 or M31)

[bookmark: _Toc90241085][bookmark: _Toc90280833][bookmark: _Toc90241086][bookmark: _Toc90280834][bookmark: _Toc90241087][bookmark: _Toc90280835][bookmark: _Toc90629811][bookmark: _Toc221176498]Financial provisions
General Principles
Distribution of Financial Contribution
The financial contribution of the Granting Authority to the Project shall be distributed by the Coordinator according to:
the Consortium Plan 
the approval of reports by the Granting Authority, and
the provisions of payment in Section 8.2.
A Beneficiary shall be funded only for its tasks carried out in accordance with the Consortium Plan. 
Justifying Costs
In accordance with its own usual accounting and management principles and practices, each Beneficiary shall be solely responsible for justifying its costs (and those of its Affiliated Entities, if any) with respect to the Project towards the Granting Authority. Neither the Coordinator nor any of the other Beneficiaries shall be in any way liable or responsible for such justification of costs towards the Granting Authority.
Funding Principles
A Beneficiary that spends less than its allocated share of the budget as set out in the Consortium Plan or – in case of reimbursement via unit costs - implements less units than foreseen in the Consortium Plan will be funded in accordance with its units/actual duly justified eligible costs only.
A Beneficiary that spends more than its allocated share of the budget as set out in the Consortium Plan will be funded only in respect of duly justified eligible costs up to an amount not exceeding that share.
The Consortium redistributes the allocated budget in the way described below:

A. Contributions for seconded staff members 
A.1 Top-up allowance
Remains exactly as in Grant Agreement. The secondment hosting the Associated partners are counted towards the hosts as in the Grant Agreement.

B. Institutional contributions
B.1 Research, training and networking contribution
The funding is re-distributed in the following way:
a) 300 EUR/person-month for each outgoing secondment (sending institution);
b) 500 EUR/person-month for each incoming secondment (hosting institution), as a solidarity contribution aimed at rebalancing the consortium’s financial sustainability. 
c) Specific arrangement in support of specific activities as agreed within the Consortium.

The specific arrangements are the following:
 CU – 8,000 EUR in support of D2.1 and D2.2
NKP – 12,000 EUR in support of S1.1–4 (3,000 EUR/week)
UCAM – 12,000 EUR in support of S2.1–2, S3.1–2 (3,000 EUR/week)
UOx – 6,400 EUR in support of the Papyri Conservation workshops (S1.5 and S1.6; hosting 8 secondments x 800 EUR)
QMUL – 7,000 in support of D3.2
OEAW – 7,000 in support of D3.1 
UNIFI – 3,000 EUR in support of papyrology training (1 week)
UHEI – 9,000 EUR in support of S1.2 (3,000 EUR/week)
UHAM – 3,000 EUR in support of training (1 week)
UWr – 3,000 EUR in support of manuscript training (1 week)
KLN – 36,300 EUR in support of the substantial number of hosting mobilities, in order to hire an institutional coordinator (hosting 121 secondments x 300 EUR) 

The remaining funding, 122,300EUR, is considered part of the common PAMELA budget. It will be retained by the coordinator and allocated for the benefit of the project based on decisions made by the Steering Committee, specifically to:
· Support collaboration with Associate Partners (500 EUR per hosting secondment, plus mobility costs for participation in project meetings and events)
· Support early-career researchers and their participation in summer schools and training activities
· Support the production of project deliverables

Any remaining unspent budget will be distributed among the project partners.

	Beneficiary 
	Total 
outgoing 
	Total 
hosting 
	Outgoing 
support 
	Hosting support 
	Specific 
arrangements
	Re-distributed 
training budget 

	CU 
	176
	27
	 52 800,00 
	 13 500,00 
	 8 000,00 
	 74 300,00 

	NKP 
	37
	19
	 11 100,00 
	 9 500,00 
	 12 000,00 
	 32 600,00 

	UCAM 
	10
	26
	 3 000,00 
	 13 000,00 
	 12 000,00 
	 28 000,00 

	UOx 
	10
	24
	 3 000,00 
	 12 000,00 
	 6 400,00 
	 21 400,00 

	QMUL 
	7
	7
	 2 100,00 
	 3 500,00 
	 7 000,00 
	 12 600,00 

	OEAW 
	16
	0
	 4 800,00 
	 -   
	 7 000,00 
	 11 800,00 

	UNIFI 
	16
	4
	 4 800,00 
	 2 000,00 
	 3 000,00 
	 9 800,00 

	UHEI 
	23
	12
	 6 900,00 
	 6 000,00 
	 9 000,00 
	 21 900,00 

	UHAM 
	11
	9
	 3 300,00 
	 4 500,00 
	 3 000,00 
	 10 800,00 

	UWr 
	18
	9
	 5 400,00 
	 4 500,00 
	 3 000,00 
	 12 900,00 

	UWar 
	17
	4
	 5 100,00 
	 2 000,00 
	-
	 7 100,00 

	KLN 
	19
	121
	 5 700,00 
	 60 500,00 
	 36 300,00 
	 102 500,00

	Common pot
	
	
	
	
	
	122 300,00



 
B.2 Management and indirect contribution
The coordinator retains 30% of the management costs for the overall project management, reporting, organization of the mid-term meeting, support for the production of project deliverables and support for the Associate partners of the project.

	Beneficiary
	Redistributed budget

	CU 
	 231 200,00   

	NKP 
	 25 900,00   

	UCAM 
	 7 000,00   

	UOx 
	 7 000,00   

	QMUL 
	 4 900,00   

	OEAW 
	 11 200,00   

	UNIFI 
	 11 200,00   

	UHEI 
	 16 100,00   

	UHAM 
	 7 700,00   

	UWr 
	 12 600,00   

	UWar 
	 11 900,00   

	KLN 
	 13 300,00   



Any changes to the budget, including expenses from the Consortium joint budget, shall require prior recommendation or approval by the Steering Committee. 
 
The Coordinator remains responsible for ensuring compliance with the Grant Agreement and may execute payments in line with Grant Agreement and provisions in the Consortium Agreement obligations even if the Steering Committee recommendation is pending, provided such actions are properly documented.
Excess payments 
A Beneficiary has received excess payment
a) if the payment received from the Coordinator exceeds the amount declared or
b) if a Beneficiary has received payments but, within the last year of the Project, its real Project costs fall significantly behind the costs it would be entitled to according to the Consortium Plan.
In case a Beneficiary has received excess payment, the Beneficiary has to inform the Coordinator and return the relevant amount to the Coordinator without undue delay. In case no refund takes place within 30 days upon request for return of excess payment from the Coordinator, the Beneficiary is in substantial breach of the Consortium Agreement.
Amounts which are not refunded by a breaching Beneficiary and which are not due to the Granting Authority, shall be apportioned by the Coordinator to the remaining Beneficiaries pro rata according to their share of total costs of the Project as identified in the Consortium Budget, until recovery from the breaching Beneficiary is possible. The Steering Committee decides on any legal actions to be taken against the breaching Beneficiary according to Section 6.2.
Revenue
In case a Beneficiary earns any revenue that is deductible from the total funding as set out in the Consortium Plan, the deduction is only directed toward the Beneficiary earning such revenue. The other Beneficiaries’ financial share of the budget shall not be affected by one Beneficiary’s revenue. In case the relevant revenue is more than the allocated share of the Beneficiary as set out in the Consortium Plan, the Beneficiary shall reimburse the funding reduction suffered by other Beneficiaries. 
Financial Consequences of the termination of the participation of a Beneficiary
A Beneficiary leaving the consortium shall refund to the Coordinator any payments it has received except the amount of contribution accepted by the Granting Authority or another contributor.
In addition, a Beneficiary declared to be a Defaulting Party shall, within the limits specified in Section 5.2 of this Consortium Agreement, bear any reasonable and justifiable additional costs occurring to the other Beneficiaries in order to perform the leaving Beneficiary’s task and necessary additional efforts to fulfil them as a consequence of the Beneficiary leaving the consortium. The Steering Committee should agree on a procedure regarding additional costs which are not covered by the Defaulting Party or the Mutual Insurance Mechanism.
[bookmark: _Toc90241090][bookmark: _Toc90241091][bookmark: _Ref90241284][bookmark: _Ref90241319][bookmark: _Ref90241945]Payments
Payments to Beneficiaries are the exclusive task of the Coordinator
In particular, the Coordinator shall:
· notify the Beneficiary concerned promptly of the date and composition of the amount transferred to its bank account, giving the relevant references 
· perform diligently its tasks in the proper administration of any funds and in maintaining financial accounts
 Distribution of payments
The total amount of the pre-financing payment from the European Commission will be of 1 172 340,00 EUR (one million one hundred seventy-two thousand three hundred forty EUR). An amount of 90 180,00 EUR (ninety thousand one hundred eighty EUR) is retained from the pre-financing payment by the European Commission for the Mutual Insurance Mechanism. The remaining pre-financing amount of 1 082 160,00 EUR (one million eighty-two thousand one hundred sixty EUR) will be distributed among the Parties proportionally to their redistributed maximum grant amount for the project, in accordance to Table 4. 
	Beneficiary 
	A.1 Top-up allowance
	B.1 Research, training and networking
 contribution
	B.2 Management and indirect contribution
	Total
	Pre-financing payment 60%

	CU 
	476 960,00 
	 74 300,00 
	 231 200,00 
	 782 460,00 
	 469 476,00   

	NKP 
	100 270,00 
	 32 600,00 
	 25 900,00 
	 158 770,00 
	 95 262,00   

	UCAM 
	27 100,00 
	 28 000,00 
	 7 000,00 
	 62 100,00 
	 37 260,00   

	UOx 
	27 100,00 
	 21 400,00 
	 7 000,00 
	 55 500,00 
	 33 300,00   

	QMUL 
	18 970,00 
	 12 600,00 
	 4 900,00 
	 36 470,00 
	 21 882,00   

	OEAW 
	43 360,00 
	 11 800,00 
	 11 200,00 
	 66 360,00 
	 39 816,00   

	UNIFI 
	43 360,00 
	 9 800,00 
	 11 200,00 
	 64 360,00 
	 38 616,00   

	UHEI 
	62 330,00 
	 21 900,00 
	 16 100,00 
	 100 330,00 
	 60 198,00   

	UHAM 
	29 810,00 
	 10 800,00 
	 7 700,00 
	 48 310,00 
	 28 986,00   

	UWr 
	48 780,00 
	 12 900,00 
	 12 600,00 
	 74 280,00 
	 44 568,00   

	UWar 
	46 070,00 
	 7 100,00 
	 11 900,00 
	 65 070,00 
	 39 042,00   

	KLN 
	51 490,00 
	 102 500,00 
	 13 300,00 
	 167 290,00 
	 100 374,00   

	Common pot
	
	122 300,00 
	
	 122 300,00 
	



The transfer of the initial pre-financing, the additional pre-financings (if any) and interim payments to Beneficiaries will be handled in accordance with Article 22.1. and Article 7 of the Grant Agreement following payment schedule set out in the Grant Agreement.
Funding of costs included in the Consortium Plan will be paid by the Coordinator to the Beneficiaries after receipt of payments from the Granting Authority in separate instalments.
[bookmark: _Toc90241093][bookmark: _Toc90280837][bookmark: _Ref90285636][bookmark: _Toc90629812][bookmark: _Toc221176499]Results
Ownership of Results
Results are owned by the Party that generates them.
[bookmark: _Toc90241096]Joint ownership
Joint ownership is governed by Grant Agreement Article 16.4 and its Annex 5, Section Ownership of results, with the following additions:
Unless otherwise agreed:
each of the joint owners shall be entitled to use their jointly owned Results for non-commercial research and teaching activities on a royalty-free basis, and without requiring the prior consent of the other joint owner(s). 
each of the joint owners shall be entitled to otherwise Exploit the jointly owned Results and to grant non-exclusive licenses to third parties (without any right to sub-license), if the other joint owners are given: (a) at least 45 calendar days advance notice; and (b) fair and reasonable compensation.
The joint owners shall agree on all protection measures and the division of related cost in advance.
[bookmark: _Toc90241098][bookmark: _Ref90241565]Transfer of Results
 
Each Party may transfer ownership of its own Results, including its share in jointly owned Results, following the procedures of the Grant Agreement Article 16.4 and its Annex 5, Section Transfer and licensing of results, sub-section “Transfer of ownership”.
[bookmark: _Ref90241270] 
Each Party may identify specific third parties it intends to transfer the ownership of its Results to in Attachment (3) of this Consortium Agreement. The other Parties hereby waive their right to prior notice and their right to object to such a transfer to listed third parties according to the Grant Agreement Article 16.4 and its Annex 5, Section Transfer of licensing of results, sub-section “Transfer of ownership”, 3rd paragraph.
 
The transferring Party shall, however, at the time of the transfer, inform the other Parties of such transfer and shall ensure that the rights of the other Parties under the Consortium Agreement and the Grant Agreement will not be affected by such transfer. Any addition to Attachment (7) after signature of this Consortium Agreement requires a decision of the Steering Committee.
 
The Parties recognise that in the framework of a merger or an acquisition of an important part of its assets, it may be impossible under applicable EU and national laws on mergers and acquisitions for a Party to give at least 45 calendar days prior notice for the transfer as foreseen in the Grant Agreement.
 
The obligations above apply only for as long as other Parties still have - or still may request - Access Rights to the Results.
[bookmark: _Toc90241100][bookmark: _Ref90241384]Dissemination
 
For the avoidance of doubt, the confidentiality obligations set out in Section 10 apply to all dissemination activities described in this Section 8.4 as far as Confidential Information is involved.
Dissemination of own (including jointly owned) Results
 
During the Project and for a period of 1 year after the end of the Project, the dissemination of own Results by one or several Parties including but not restricted to publications and presentations, shall be governed by the procedure of Article 17.4 of the Grant Agreement and its Annex 5, Section Dissemination, subject to the following provisions.
Prior notice of any planned publication shall be given to the other Parties at least 15 calendar days before the publication. Any objection to the planned publication shall be made in accordance with the Grant Agreement by written notice to the Coordinator and to the Party or Parties proposing the dissemination within 15 calendar days after receipt of the notice. If no objection is made within the time limit stated above, the publication is permitted.
 
An objection is justified if
a) the protection of the objecting Party's Results or Background would be adversely affected, or
b) the objecting Party's legitimate interests in relation to its Results or Background would be significantly harmed, or
c) the proposed publication includes Confidential Information of the objecting Party.
The objection has to include a precise request for necessary modifications.
 
If an objection has been raised the involved Parties shall discuss how to overcome the justified grounds for the objection on a timely basis (for example by amendment to the planned publication and/or by protecting information before publication) and the objecting Party shall not unreasonably continue the opposition if appropriate measures are taken following the discussion.
 
The objecting Party can request a publication delay of not more than 90 calendar days from the time it raises such an objection. After 90 calendar days the publication is permitted, provided that the objections of the objecting Party have been addressed.
Dissemination of another Party’s unpublished Results or Background
A Party shall not include in any dissemination activity another Party's Results or Background without obtaining the owning Party's prior written approval, unless they are already published.
Cooperation obligations
The Parties undertake to cooperate to allow the timely submission, examination, publication and defense of any dissertation or thesis for a degree that includes their Results or Background subject to the confidentiality and publication provisions agreed in this Consortium Agreement.
Use of names, logos or trademarks
Nothing in this Consortium Agreement shall be construed as conferring rights to use in advertising, publicity or otherwise the name of the Parties or any of their logos or trademarks without their prior written approval. This does not refer to dissemination material for the Project itself and its activities (such as, but not limited to, the website, brochures, posters etc.). The Parties consent to their names and logos being used for the Project dissemination purposes.
[bookmark: _Toc90241102][bookmark: _Toc90280839][bookmark: _Toc90241103][bookmark: _Toc90280840][bookmark: _Ref90241428][bookmark: _Toc90629813][bookmark: _Toc221176500]Access Rights
Background included
 
In Attachment 1, the Parties have identified and agreed on the Background for the Project and have also, where relevant, informed each other that Access to specific Background is subject to legal restrictions or limits.
Anything not identified in Attachment 1 shall not be the object of Access Right obligations regarding Background.
 
Any Party may add additional Background to Attachment 1 during the Project provided they give written notice to the other Parties. However, approval of the Steering Committee is needed should a Party wish to modify or withdraw its Background in Attachment 1.
[bookmark: _Toc90241106][bookmark: _Ref90242064][bookmark: _Ref90242138]General Principles 
 
Each Party shall implement its tasks in accordance with the Consortium Plan and shall bear sole responsibility for ensuring that its acts within the Project do not knowingly infringe third party property rights.
 
Any Access Rights granted exclude any rights to sublicense unless expressly stated otherwise.
 
Access Rights shall be free of any administrative transfer costs.
 
Access Rights are granted on a non-exclusive basis.
 
Results and Background shall be used only for the purposes for which Access Rights to it have been granted.
 
All requests for Access Rights shall be made in writing. The granting of Access Rights may be made conditional on the acceptance of specific conditions aimed at ensuring that these rights will be used only for the intended purpose and that appropriate confidentiality obligations are in place.
 
The requesting Party must show that the Access Rights are Needed.
[bookmark: _Toc90241108]Access Rights for implementation
Access Rights to Results and Background Needed for the performance of the own work of a Party under the Project shall be granted on a royalty-free basis.
[bookmark: _Toc90241110][bookmark: _Toc90241111][bookmark: _Ref90242030]Access Rights for Exploitation
Access Rights to Results
Access Rights to Results if Needed for Exploitation of a Party's own Results shall be granted on Fair and Reasonable conditions.
Access rights to Results for internal research and for teaching activities shall be granted on a royalty-free basis.
 
Access Rights to Background if Needed for Exploitation of a Party’s own Results, shall be granted on Fair and Reasonable conditions.
[bookmark: _Ref90241419] 
A request for Access Rights may be made up to twelve months after the end of the Project.
[bookmark: _Toc90241113]Access Rights for entities under the same control
Entities under the same control have Access Rights under the conditions of the Grant Agreement Article 16.4 and its Annex 5, Section "Access rights to results and background”, sub-section “Access rights for entities under the same control”.
Such Access Rights must be requested by the entity under the same control from the Party that holds the Background or Results. Alternatively, the Party granting the Access Rights may individually agree with the [Beneficiary / Party] requesting the Access Rights to have the Access Rights include the right to sublicense to the latter's entity under the same control. Access Rights to an entity under the same control shall be granted on Fair and Reasonable conditions and upon written bilateral agreement.
Entities under the same control which obtain Access Rights in return fulfil all confidentiality obligations accepted by the Parties under the Grant Agreement or this Consortium Agreement as if such entities were Parties.
Access Rights may be refused to entities under the same control if such granting is contrary to the legitimate interests of the Party which owns the Background or the Results.
Access Rights granted to any entity under the same control are subject to the continuation of the Access Rights of the [Beneficiary / Party] with whom it is under the same control, and shall automatically terminate upon termination of the Access Rights granted to such [Beneficiary / Party].
Upon cessation of the status as an entity under the same control, any Access Rights granted to such former entity under the same control shall lapse.
Further arrangements with entities under the same control may be negotiated in separate agreements.
[bookmark: _Toc90241115]Additional Access Rights
For the avoidance of doubt any grant of Access Rights not covered by the Grant Agreement or this Consortium Agreement shall be at the absolute discretion of the owning Party and subject to such terms and conditions as may be agreed between the owning and receiving Parties.
[bookmark: _Toc90241117][bookmark: _Toc90241118]Access Rights for Parties entering or leaving the consortium
New Parties entering the consortium 
As regards Results developed before the accession of the new Party, the new Party will be granted Access Rights on the conditions applying for Access Rights to Background.
Parties leaving the consortium
Access Rights granted to a leaving Party
[bookmark: _Ref90241536]Defaulting Party
Access Rights granted to a Defaulting Party and such Party's right to request Access Rights shall cease immediately upon receipt by the Defaulting Party of the formal notice of the decision of the Steering Committee to terminate its participation in the consortium.
[bookmark: _Ref90241406]Non-defaulting Party
A non-defaulting Party leaving voluntarily and with the other Parties' consent shall have Access Rights to the Results developed until the date of the termination of its participation.
It may request Access Rights within the period of time specified in Section 9.4.3.
Access Rights to be granted by any leaving Party
Any Party leaving the Project shall continue to grant Access Rights pursuant to the Grant Agreement and this Consortium Agreement as if it had remained a Party for the whole duration of the Project.
[bookmark: _Toc90241120]Specific Provisions for Access Rights to Software
For the avoidance of doubt, the general provisions for Access Rights provided for in this Section 9 are applicable also to Software.
Parties’ Access Rights to Software do not include any right to receive source code or object code ported to a certain hardware platform or any right to receive respective Software documentation in any particular form or detail, but only as available from the Party granting the Access Rights.
[bookmark: _Toc90241122][bookmark: _Toc90280842][bookmark: _Toc90404936][bookmark: _Ref90241368][bookmark: _Toc90629814][bookmark: _Toc221176501]Non-disclosure of information
[bookmark: _Toc90241124] 
All information in whatever form or mode of communication, which is disclosed by a Party (the “Disclosing Party”) to any other Party (the “Recipient”) in connection with the Project during its implementation and which has been explicitly marked as “confidential” at the time of disclosure, or when disclosed orally has been identified as confidential at the time of disclosure and has been confirmed and designated in writing within 15 calendar days from oral disclosure at the latest as confidential information by the Disclosing Party, is “Confidential Information”.
[bookmark: _Toc90241126][bookmark: _Toc90241127] 
The Recipient hereby undertakes in addition and without prejudice to any commitment on non-disclosure under the Grant Agreement, for a period of 5 years after the final payment of the Granting Authority:
not to use Confidential Information otherwise than for the purpose for which it was disclosed;
not to disclose Confidential Information without the prior written consent by the Disclosing Party;
to ensure that internal distribution of Confidential Information by a Recipient shall take place on a strict need-to-know basis; and
to return to the Disclosing Party, or destroy, on request all Confidential Information that has been disclosed to the Recipients including all copies thereof and to delete all information stored in a machine-readable form to the extent practically possible. The Recipients may keep a copy to the extent it is required to keep, archive or store such Confidential Information because of compliance with applicable laws and regulations or for the proof of on-going obligations provided that the Recipient complies with the confidentiality obligations herein contained with respect to such copy.
[bookmark: _Toc90241129] 
The Recipient shall be responsible for the fulfilment of the above obligations on the part of its employees or third parties involved in the Project and shall ensure that they remain so obliged, as far as legally possible, during and after the end of the Project and/or after the termination of the contractual relationship with the employee or third party.
[bookmark: _Toc90241131] 
The above shall not apply for disclosure or use of Confidential Information, if and in so far as the Recipient can show that:
the Confidential Information has become or becomes publicly available by means other than a breach of the Recipient’s confidentiality obligations;
the Disclosing Party subsequently informs the Recipient that the Confidential Information is no longer confidential;
the Confidential Information is communicated to the Recipient without any obligation of confidentiality by a third party who is to the best knowledge of the Recipient in lawful possession thereof and under no obligation of confidentiality to the Disclosing Party;
the disclosure or communication of the Confidential Information is foreseen by provisions of the Grant Agreement;
the Confidential Information, at any time, was developed by the Recipient completely independently of any such disclosure by the Disclosing Party; 
the Confidential Information was already known to the Recipient prior to disclosure, or
the Recipient is required to disclose the Confidential Information in order to comply with applicable laws or regulations or with a court or administrative order, subject to the provision Section 10.7 hereunder.
[bookmark: _Toc90241133] 
The Recipient shall apply the same degree of care with regard to the Confidential Information disclosed within the scope of the Project as with its own confidential and/or proprietary information, but in no case less than reasonable care
[bookmark: _Toc90241135] 
Each Recipient shall promptly inform the relevant Disclosing Party by written notice of any unauthorised disclosure, misappropriation or misuse of Confidential Information after it becomes aware of such unauthorised disclosure, misappropriation or misuse.
[bookmark: _Toc90241137][bookmark: _Ref90241448] 
If any Recipient becomes aware that it will be required, or is likely to be required, to disclose Confidential Information in order to comply with applicable laws or regulations or with a court or administrative order, it shall, to the extent it is lawfully able to do so, prior to any such disclosure
notify the Disclosing Party, and
comply with the Disclosing Party’s reasonable instructions to protect the confidentiality of the information.
[bookmark: _Toc90241139][bookmark: _Toc90280844][bookmark: _Toc90404938][bookmark: _Toc90241140][bookmark: _Toc90280845][bookmark: _Toc90404939][bookmark: _Toc90241141][bookmark: _Toc90280846][bookmark: _Toc90404940][bookmark: _Toc90629815][bookmark: _Toc221176502]Miscellaneous
Attachments, inconsistencies and severability
This Consortium Agreement consists of this core text and:
Attachment 1 (Background included) 
Attachment 2 (Accession document)
Attachment 3 (Secondment Agreement)
In case the terms of this Consortium Agreement are in conflict with the terms of the Grant Agreement, the terms of the latter shall prevail. In case of conflicts between the attachments and the core text of this Consortium Agreement, the latter shall prevail.
Should any provision of this Consortium Agreement become invalid, illegal or unenforceable, it shall not affect the validity of the remaining provisions of this Consortium Agreement. In such a case, the Parties concerned shall be entitled to request that a valid and practicable provision be negotiated that fulfils the purpose of the original provision.
[bookmark: _Toc90241144]No representation, partnership or agency
Except as otherwise provided in Section 6.3.4, no Party shall be entitled to act or to make legally binding declarations on behalf of any other Party or of the consortium. Nothing in this Consortium Agreement shall be deemed to constitute a joint venture, agency, partnership, interest grouping or any other kind of formal business grouping or entity between the Parties.
Formal and written notices
Any notice to be given under this Consortium Agreement shall be addressed to the recipients as listed in the most current address list kept by the Coordinator.
Any change of persons or contact details shall be immediately communicated to the Coordinator by written notice. The address list shall be accessible to all Parties.
Formal notices:
If it is required in this Consortium Agreement that a formal notice, consent or approval shall be given, such notice shall be signed by an authorised representative of a Party and shall either be served personally or sent by mail with recorded delivery with acknowledgement of receipt.
Written notice:
Where written notice is required by this Consortium Agreement, this is fulfilled also by other means of communication such as e-mail.
[bookmark: _Toc90241147][bookmark: _Toc90241148][bookmark: _Ref90241547]Assignment and amendments
Except as set out in Section 9.3, no rights or obligations of the Parties arising from this Consortium Agreement may be assigned or transferred, in whole or in part, to any third party without the other Parties’ prior formal approval.
Amendments and modifications to the text of this Consortium Agreement not explicitly listed in 6.2.1 require a separate written agreement to be signed between all Parties.
[bookmark: _Toc90241150]Mandatory national law
Nothing in this Consortium Agreement shall be deemed to require a Party to breach any mandatory statutory law under which the Party is operating.
Language
This Consortium Agreement is drawn up in English, which language shall govern all documents, notices, meetings, arbitral proceedings and processes relative thereto.
[bookmark: _Toc90241153]Applicable law
This Consortium Agreement shall be construed in accordance with and governed by the laws of Belgium excluding its conflict of law provisions.
[bookmark: _Toc90241155][bookmark: _Ref90241834]Settlement of disputes
The Parties shall endeavour to settle their disputes amicably.
All disputes arising out of or in connection with this Consortium Agreement, which cannot be solved amicably, shall be finally settled by the courts of Brussels.


[bookmark: _Toc90241157][bookmark: _Toc90280848][bookmark: _Toc90404942][bookmark: _Toc90241158][bookmark: _Toc90280849][bookmark: _Toc90404943][bookmark: _Toc90241159][bookmark: _Toc90280850][bookmark: _Toc90404944][bookmark: _Toc90241160][bookmark: _Toc90280851][bookmark: _Toc90404945][bookmark: _Toc90241161][bookmark: _Toc90280852][bookmark: _Toc90404946][bookmark: _Toc90241162][bookmark: _Toc90280853][bookmark: _Toc90404947][bookmark: _Toc90629816][bookmark: _Toc221176503]Signatures
[bookmark: _Toc90629817]IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement:
 
We the undersigned legal representatives of the UNIVERZITA KARLOVA declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	UNIVERZITA KARLOVA 

	Authorized person to commit 
	Eva Lehečková 

	Title 
	Dean of the Faculty of Arts 

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 
 
We the undersigned legal representatives of the NARODNI KNIHOVNA CESKE REPUBLIKY declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	NARODNI KNIHOVNA CESKE REPUBLIKY 

	Authorized person to commit 
	 Mgr. Tomáš Foltýn

	Title 
	director 

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 
 
We the undersigned legal representatives of THE CHANCELLOR MASTERS AND SCHOLARS OF THE UNIVERSITY OF CAMBRIDGE the declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	THE CHANCELLOR MASTERS AND SCHOLARS OF THE UNIVERSITY OF CAMBRIDGE 

	Authorized person to commit 
	Susan Black 

	Title 
	Senior Contracts Manager 

	Date  
	 

	Signature 
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 
 
We the undersigned legal representatives of THE CHANCELLOR, MASTERS AND SCHOLARS OF THE UNIVERSITY OF OXFORD the declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	THE CHANCELLOR, MASTERS AND SCHOLARS OF THE UNIVERSITY OF OXFORD 

	Authorized person to commit 
	Eleanor Salmon 

	Title 
	Research Contracts Lead, Research Services 

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 

 
We the undersigned legal representatives of the QUEEN MARY UNIVERSITY OF LONDON declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	QUEEN MARY UNIVERSITY OF LONDON 

	Authorized person to commit 
	Gerry Collins 

	Title 
	Head of Pre-award  

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 

 
We the undersigned legal representatives of the OESTERREICHISCHE AKADEMIE DER WISSENSCHAFTEN declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	OESTERREICHISCHE AKADEMIE DER WISSENSCHAFTEN 

	Authorized person to commit 
	Mag. Dr. iur. Bedanna Bapuly 

	Title 
	Legal representative, Grant Services 

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 

 
We the undersigned legal representatives of the UNIVERSITA DEGLI STUDI DI FIRENZE declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	UNIVERSITA DEGLI STUDI DI FIRENZE 

	Authorized person to commit 
	Prof. Simone Magherini 

	Title 
	Director of  Department of Literature and Philosophy

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 

 
We the undersigned legal representatives of the RUPRECHT-KARLS-UNIVERSITAET HEIDELBERG declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	RUPRECHT-KARLS-UNIVERSITAET HEIDELBERG 

	Authorized person to commit 
	 Susanne Geiselhart

	Title 
	Head of Legal and Structural Issues of Research Funding 

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 

 
We the undersigned legal representatives of the UNIVERSITY OF HAMBURG declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	UNIVERSITY OF HAMBURG 

	Authorized person to commit 
	Dr. Corinna Prang 

	Title 
	Section Manager

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 

 
We the undersigned legal representatives of the UNIWERSYTET WROCLAWSKI declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	UNIWERSYTET WROCLAWSKI 

	Authorized person to commit 
	Prof. Robert Olkiewicz 

	Title 
	Rector 

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 

We the undersigned legal representatives of the UNIWERSYTET WARSZAWSKI declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	UNIWERSYTET WARSZAWSKI 

	Authorized person to commit 
	Prof. dr hab. Zygmunt Lalak  

	Title 
	Vice-rector for Research 

	Date  
	 

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


IN WITNESS WHERE OF, the Parties have executed this Consortium Agreement: 

 
We the undersigned legal representatives of the CHORHERRENSTIFT KLOSTERNEUBURG declare that we will implement the Project within the Horizon Europe Marie Skłodowska-Curie Action – Staff Exchanges (SE) Scheme, Call identifier: HORIZON-MSCA-2024-SE-01, Grant Agreement No. 101236480 – Acronym: PAMELA in accordance with provisions of the Grant Agreement, of this Consortium Agreement and in line with the Description of Work (Annex I to the Grant Agreement). 
 
 
	Beneficiary institution’s name 
	CHORHERRENSTIFT KLOSTERNEUBURG 

	Authorized person to commit 
	MMag. Dr. Martin Haltrich 

	Title 
	Stiftsbibliothekar

	Date  
	

	Signature  
	 

	Stamp 
 
 
 
 
 
	 


 
 


[bookmark: _Toc221176504]Attachment 1: Background 
According to the Grant Agreement (Article 16.1) Background is defined as “data, know-how or information (…) that is (…) needed to implement the Action or exploit the results”. Because of this need, Access Rights have to be granted in principle, but Parties must identify and agree amongst them on the Background for the Project. This is the purpose of this attachment.
As to UNIVERZITA KARLOVA (CUNI), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of CUNI is needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to NARODNI KNIHOVNA CESKE REPUBLIKY (NKP), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of NKP is Needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to THE CHANCELLOR MASTERS AND SCHOLARS OF THE UNIVERSITY OF CAMBRIDGE (UCAM), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of UCAM is Needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to THE CHANCELLOR, MASTERS AND SCHOLARS OF THE UNIVERSITY OF OXFORD (UOx) it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of UOx is needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to QUEEN MARY UNIVERSITY OF LONDON (QMUL), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of QMUL is Needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to OESTERREICHISCHE AKADEMIE DER WISSENSCHAFTEN (OEAW), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of OEAW is Needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to UNIVERSITA DEGLI STUDI DI FIRENZE (UNIFI), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of UNIFI is needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to RUPRECHT-KARLS-UNIVERSITAET HEIDELBERG (UHEI), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of UHEI is Needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to UNIVERSITY OF HAMBURG (UHAM), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of UHAM is Needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to UNIWERSYTET WROCLAWSKI (UWr), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of UWr is needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to UNIWERSYTET WARSZAWSKI (UWar), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of UWar is needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
As to CHORHERRENSTIFT KLOSTERNEUBURG (KLN), it is agreed between the Parties that, to the best of their knowledge, no data, know-how or information of KLN is Needed by another Party for implementation of the Project (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights to background and results for implementing the action”) or Exploitation of that other Party’s Results (Article 16.1 and its Annex 5 Grant Agreement, Section “Access rights to results and background”, sub-section “Access rights for exploiting the results”).
This represents the status at the time of signature of this Consortium Agreement. 



[bookmark: _Toc90629818][bookmark: _Toc221176505]Attachment 2: Accession document
ACCESSION
of a new Party to
PAMELA Consortium Agreement, version […, YYYY-MM-DD]
[OFFICIAL NAME OF THE NEW PARTY AS IDENTIFIED IN THE Grant Agreement]
hereby consents to become a Party to the Consortium Agreement identified above and accepts all the rights and obligations of a Party starting [date].
[OFFICIAL NAME OF THE COORDINATOR AS IDENTIFIED IN THE Grant Agreement]
hereby certifies that the consortium has accepted in the meeting held on [date] the accession of [the name of the new Party] to the consortium starting [date].

[Date and Place]
[INSERT NAME OF THE NEW PARTY]
Signature(s)
Name(s)
Title(s)

[Date and Place]
[INSERT NAME OF THE COORDINATOR]
Signature(s) 
Name(s) 
Title(s)
[101236480 – PAMELA] Consortium Agreement, version 1.0, 10/12/2025
[bookmark: _Toc413431109][bookmark: _Toc290300736]

[bookmark: _Toc221176506]Attachment 3: List of third parties for simplified transfer according to Section 9.3.2.

For UCAM:
For The Chancellor, Masters, and Scholars of the University of Cambridge:
• Cambridge Enterprise Limited, whose registered address is at The Old Schools, Trinity Lane, 
Cambridge, Cambridgeshire, CB2 1TN, United Kingdom.
• A wholly owned subsidiary of the University of Cambridge
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