LOGFRAME PLANNING MATRIX

| Project Title: Institutional support for certification and control of plant material in BiH |  |  | Programme number: |  |
| --- | --- | --- | --- | --- |
|  |  |  | Total Budget | Czech contribution: |
| Overall Objective | Objectively verifiable indicators | Sources of verification |  |  |
| - Ability to fulfil the demands resulting from EU standards, including the adoption of an effective system of plant propagating material certification including strenghtening of oficial control in BiH | Well established system of plant propagating material certification (2Q/2016) | Country Summary Evaluation Report (produced by the independent external consultant) Final report |  |  |
| Project Purpose | ##### Objectively verifiable indicators | Sources of verification | Assumptions |  |
| To establish a system of official control and certification within the plant propagating material which is common in EU Member States including the implementation of the principles of EC legislation which will help to strengthen certainty of both consumers and entrepreneurs. | - Harmonized legislation and methodology in the area of certification (1Q/ 2016) - Completed institutional structure in the field of official control (4Q/2015) - Increased confidence of consumers on the basis of transparent communication with public (continuously) | - Progress reports on project running provided by CISTA in cooperation with beneficiary - Reports of independent evaluating bodies - Annual implementation report | The beneficiary administration appoints the Project Leader and all relevant counterparts and makes available the staff that will be involved during the project implementation. |  |
| Results | Objectively verifiable indicators | Sources of verification | Assumptions |  |
| 1) Optimized state administration included trained staff 2) Renewed and harmonized legislation 3) Fully functional system for the registration of new varieties 4) Established control system on propagating material 5) Improved plant nursery production | 1.1 Optimized complex organizational structure of official control in the area of certification submitted by government order (1Q/2015) 1.2 Well-trained staff of all involved state bodies performing state administration - final evaluation of gained knowledge (at least 30 people) 2Q/2015 1.3 Informed expert public on optimized state administration (at least 40 participants), substantiated by attendance list and filled surveys 3 Q2015 2.1 Legislation fully harmonized with EU legislation submitted by PHPA(1Q 2015) 2.2 At least 30 informed and trained staff on amended legislation - final evaluation of gained knowledge 3.1 Modified process of new varieties registration according EU legislation in operation (2Q2015) 3.2.At least 20 informed and trained staff of state administration involved in the process of registration of new varieties - final evaluation of gained knowledge (3Q/2015) 4.1 Renewed register of persons in operation (1Q/2015) 4.2 At least 20 informed and trained staff of state administration involved in the process of registration (1Q2015) - final evaluation of gained knowledge 5.1 The number of nurseries trained in new technologies and EU standards (At least 10 - 2Q/2015) evaluated by Progress report 5.2 At least 2 nurseries are producing certified disease and virus free plant materials according to EU standards evaluated by Progress report (2Q/2015) | - Accepted draft by PHPA - List of attendance, training materials - Knowledge evaluation reports - List of attendance, photos - Submitted (approved) legislation to the parliament by PHPA - Monthly reports from different institutions - Complete draft of the of the process - Complete draft of the renewed register - Monthly reports from different institutions - Government reports - Progress Reports | - Qualified staff of BiH administration and committed producers, availability of national funds for future financing. 2 ) Passing of proposed legislation by beneficiary Commitment relevant authorities towards the legislation process 3) Availability of national funds for financing, continuation in international co-operation in this field 4) Availability of national funds for financing, 5) Functional system of official control, availability of financial sources |  |
| Activities | Means |  | Assumptions |  |
| 1.1 Detailed analysis and assessment , subsequent draft of the capacity optimization structure of the official control system; 1.2 Tailor made training programme; 1.3 Advice and coaching sessions, sharing of experience; 1.4 Seminars and workshops; 1.5 Study visits; 2.1 Detailed analyses and assessment, subsequent draft of the legislation; 2.2 Advice and coaching sessions, sharing of experience; 2.3 Seminars and workshops; 3.1 Establishment of the modified process of new varieties registration; 3.2 Working out of relevant manuals, procedures; 3.3 Advice and coaching sessions, sharing of experience; 3.4 Seminars and workshops; 3.5 Study visits; 4.1 Detailed analyses and assessment, subsequent draft of renewed register; 4.2 ; Working out of relevant manuals, procedures; 4.3 Advice and coaching sessions; 4.4 Seminars and workshops; 5.1. Advice and coaching sessions, sharing of experience; 5.2 Seminars, workshops and conferences; 5.3 Study visits. | - One contract - One project leader - One local coordinator - 4 component leaders - Up to 20 short-term experts (800 man- days) |  | - Qualified staff of BiH administration and committed producers, common ground of both main entities - Commitment of the relevant authorities towards the legislation process, common ground of both main entities - Establishing of special department on variety registration by PHPA - Qualified staff of BiH administration. effective co-operation, involved producers and NGO’s - Commitment of relevant producers |  |
| Preconditions - Capability of supervisors and experts - Key staff in beneficiary institutions appointed. - Well defined future needs in the field of of plant production material certification |  |  |  |  |