Roční plán činnosti na rok 2016

Název projektu: Institutional support for certification and control of plant material

Číslo projektu: CZDA-RO-BA-2013-3-31192

Celkový rozpočet projektu: 10 338 500,-

Rozpočet na rok 2016: 3 292 000,-

| Výstupy | Popis aktivit | Termín realizace |
| --- | --- | --- |
| Project management | 4 Steering Com. ¨ Regular meetings with representatives of state and entity administration Regular consultations Presentation of project on the conference in Banja Luka | January, April, August, December 2016 Ad Hoc Whole year February 2016 |
| 1. Capacity building relating to the system of certification including official controls – | 3x workshop in nurseries near Mostar, Sarajevo and Banja Luka for producers and inspectors, both theoretical and practical training Preparation on common methodology for inspectors (RS and FBiH) including the workshops Study visit to the Czech Republic – The representatives of Subjects involved in the project Study visit of phyto inspectors Labs evaluation regarding the accreditation Consultations and advisory | May 2016 January, April , May 2016 May 2016 August 2016 February 2016 Whole year |
| 2. Harmonisation of the legislation in the field of national quality protection | Seminar on new EU legislation Discussion on draft of amendments on current legislation (the Act on Seed and Seedlings) Consultations and advisory | October 2016 July 2016 |
| 3. Establishing of fully functional system for the registration of new varieties | Round table on variety listing Workshop on DUS and VCU testing Consultations and advisory Study visit of experts involved in the process of registration of new varieties | September 2016 June 2016 Whole year October 2016 |
| 4. Establishing of the renewed register of persons in BiH | Seminar on the problems of register of person in the area of production, importation and marketing of propagating material () Round table on register of persons Consultations and advisory | January, August 2016 August 2016 Whole year |
| 5. Improvements in plant nursery production | 5.1 Workshops for nurseries - specific topics (mother blocks, isolates etc.) Inspection of nurseries 5.2 Consultations and advisory | May 2016 August, October 2016 Whole year |
| CELKEM požadováno na daný rok | 3 292 000,- |  |