Annual Activity Plan for 2017

Project title: Institutional support for certification and control of plant material

Project noumber: CZDA-RO-BA-2013-3-31192

Project budget: 10 338 500,-

Budget for 2017: 2 920 807,55

| Results and Activities | Description of activities | Date of realization |
| --- | --- | --- |
| Project management | - 4 x Steering Com. - Regular meetings with representatives of state and entity administration - Regular consultations - Round table on phytosanitary issues | April, June, October, December Ad Hoc Whole year May 2016 (15-19) |
| ### Capacity building relating to the system of certification including official controls - Detailed analysis and assessment, subsequent draft of the capacity optimization structure of the official control system; 1.2 Tailor made training programme; - Advice and coaching sessions, sharing of experience; - Seminars and workshops; - Study visits | Evaluation of the laboratory of the FACULTY OF AGRICULTURE, UNIVERSITY OF BANJA LUKA concerning its preparedness for accreditation according to ISO 17025 (Detection and identification of potato cyst nematodes Globodera rostochiensis and Globodera palida) Evaluation of the phytosanitary laboratories in BiH focused in compliance with valid european legislation for testing of regulated harmful organisms – quarantine bacteria of potatoes (further QBP Special workshops for nurseries and inspectors - specific topics (mother blocks of selected species.) Workshop on post control Consultations and advisory Workshop detection and identification of pine wood nematode Bursaphelenchus xylophilus and related species and monitoring of their insect vectors. Study visit for inspectors | October May August (September) Whole year April June |
| 2. Harmonisation of the legislation in the field of national quality protection 2.1 Detailed analyses and assessment, subsequent draft of the legislation; 2.2 Advice and coaching sessions, sharing of experience; 2.3 Seminars and workshops; | Discussion and preparation of draft of amendments on current legislation (the Act on Seed and Seedlings) Preparation of rule book Consultations and advisory | August – December Whole year April |
| 3. Establishing of fully functional system for the registration of new varieties 3.1 Establishment of the modified process of new varieties registration; 3.2 Working out of relevant manuals, procedures; 3.3 Advice and coaching sessions, sharing of experience; 3.4 Seminars and workshops; 3.5 Study visits; | Round table on variety listing Consultations and advisory Study visit of experts involved in the process of registration of new varieties | October 2016 Whole year August 2017 |
| 4. Establishing of the renewed register of persons in BiH 4.1 Detailed analyses and assessment, subsequent draft of renewed register; 4.2 Working out of relevant manuals, procedures; 4.3 Advice and coaching sessions; - Seminars and workshops; | Round table on register of persons Consultations and advisory Seminar on the problems of register of person in the area of production, importation and marketing of propagating material | October Whole year October |
| - Improvements in plant nursery production 5.1. Advice and coaching sessions, sharing of experience; - Seminars, workshops and conferences; - Study visits. | Advisory mission for nurseries Inspection of nurseries Workshops for nurseries and inspectors - specific topics (mother blocks of selected species.) | June September May 2015 |
| Budget for 2017 | 2 920 807,55 |  |